## 
Open Contract Analysis for the Cadillac Forest Management Unit
as of December 11, 2013
Use Page Down Key to See List of Open Sales
Nbr of
|  | Sale Expiration Status | Sales
|  | Contracts Expired | 8 | [9 empty] | Expiration | Expiration | Expiration | Expiration | Expiration
|  | 30 Days before Expiration | 7 | [9 empty] | <0 | >0 | <31 | >30 | <61
|  | 60 Days before Expiration | 0 | [9 empty] | Expiration
|  | >60 Days before Expiration | 117 | [9 empty] | >60
|  | Total | 132
|  | Contract Summary |  |  | Total | [7 empty] | Sale Number | Acres | Volume | Value | Received | Length(days)
|  | Nbr of Open Contracts |  |  | 132 | [7 empty] | > " " | > 0.00 | >0.00 | >0.00 | >0.00 | >0.00
|  | Acres of Open Contracts |  |  | 11892.8
|  | Open Contacts Cords |  |  | 200181.3
|  | Value of Open Contracts |  |  | 7603356.24
|  | Amount Received to Date |  |  | 4122775.23
|  | Amount Remaining |  |  | 3480581.01
|  | Percentage of Contract Value Received to Date |  |  | 54.22%
|  | Expiration Date Used |  |  | 2013-12-11
|  | Avg Contract Length (Years) |  |  | 3.0455
Open Timber Sale Contracts sorted by Days Before Expiration
|  |  |  | Total | Current |  | Contract | Original | Current | Days |  | Current
| Cont |  |  | Cord | Contract | Amount | Issue | Expiration | Expiration | Before |  | Contract
Sale Number | Seq | Sale Name | Acres | Volume | Value | Received | Date | Date | Date | Expiration | Purchaser Name | Length(days)
630561001 | 1 | SHADE GAP HARDWOOD | 44 | 1098.8 | 43375.36 | 43375.36 | 2011-07-15 | 2013-06-13 | 2013-06-13 | -181 | SILVER LEAF SAWMILL | 699
630271001 | 1 | ORTWEIN PINE | 46 | 535.9 | 34677.41 | 34677.41 | 2011-06-16 | 2013-06-30 | 2013-06-30 | -164 | BISBALLE FOREST PRODUCTS | 745
630281001 | 1 | PARTRIDGE PUPS ASPEN | 45 | 610.2 | 21838.15 | 21838.15 | 2011-05-23 | 2013-06-30 | 2013-06-30 | -164 | BISBALLE FOREST PRODUCTS | 769
630400901 | 1 | RECREATION RED | 105 | 1715.4 | 90383.34 | 68525.32 | 2010-06-21 | 2012-06-30 | 2013-06-30 | -164 | BISBALLE FOREST PRODUCTS | 1105
630451001 | 1 | NARROW GAUGE ASPEN | 123 | 3145.8 | 91168.49 | 91168.49 | 2011-05-20 | 2013-06-30 | 2013-06-30 | -164 | PACKAGING CORP OF AMERICA | 772
630700901 | 2 | PILEATED PARADISE | 56 | 1025 | 37608.57 | 5641.29 | 2011-06-10 | 2013-06-30 | 2013-06-30 | -164 | BISBALLE FOREST PRODUCTS | 751
630350801 | 1 | NORTH V SOUTH | 68 | 1438 | 27895.51 | 27895.5 | 2010-03-18 | 2012-09-30 | 2013-09-30 | -72 | DOYLE FOREST PRODUCTS | 1292
630420901 | 1 | HIDDEN HARDWOODS | 85 | 1629.6 | 52662.78 | 52662.78 | 2010-09-15 | 2012-09-30 | 2013-09-30 | -72 | DYERS SAWMILL | 1111
630471001 | 1 | BUCKLEY BIG DOG | 241 | 4221.6 | 192537.16 | 192537.16 | 2011-06-30 | 2013-12-13 | 2013-12-13 | 2 | LUTKE FOREST PRODS, INC. | 897
630601101 | 1 | WHITE PINE OAK MIX | 67 | 1426.8 | 29199.9 | 2919.99 | 2012-01-12 | 2013-12-13 | 2013-12-13 | 2 | DOYLE FOREST PRODUCTS | 701
630051101 | 1 | STRIPED PINE | 44 | 619.8 | 45593.16 | 4559.32 | 2011-06-30 | 2013-12-31 | 2013-12-31 | 20 | ROBERT OUTMAN | 915
630091101 | 1 | BUCK STOP ASPEN | 27 | 1180.8 | 32377.5 | 32377.5 | 2011-08-29 | 2013-12-31 | 2013-12-31 | 20 | CHRIS PARK | 855
630381001 | 1 | DEER FLY ASPEN | 66 | 841.2 | 21679.41 | 2167.94 | 2011-06-30 | 2013-12-31 | 2013-12-31 | 20 | ROBERT OUTMAN | 915
630450901 | 2 | TIGER LILY PINE | 35 | 390.4 | 5619.58 | 5619.58 | 2010-02-11 | 2012-03-31 | 2013-12-31 | 20 | HALLETT FOREST PRODUCTS | 1419
630521001 | 1 | OAK 101 | 27 | 483.8 | 6820.11 | 682.01 | 2011-06-30 | 2013-12-31 | 2013-12-31 | 20 | ROBERT OUTMAN | 915
630361001 | 1 | OCTOPUS OAK | 179 | 1807.4 | 54837.72 | 7833.96 | 2011-04-21 | 2013-03-31 | 2014-03-01 | 80 | SHAWN MUMA | 1045
630130901 | 1 | COMPARTMENT 100 OAK | 189 | 3739.4 | 129668.99 | 104118.45 | 2010-03-24 | 2013-03-31 | 2014-03-31 | 110 | SHAWN MUMA | 1468
630141001 | 1 | 118 OAK/ASPEN | 282 | 3956.6 | 123978.2 | 123978.2 | 2012-04-12 | 2014-03-31 | 2014-03-31 | 110 | CHRIS PARK | 718
630141101 | 1 | ASPEN JUNCTION | 110 | 2550.8 | 97686.1 | 68380.36 | 2011-10-19 | 2014-03-31 | 2014-03-31 | 110 | ROBERT OUTMAN | 894
630221101 | 1 | UGLY COYOTE PINE | 109 | 1273.4 | 71906.6 | 14381.32 | 2012-04-25 | 2014-03-31 | 2014-03-31 | 110 | HYDROLAKE, INC. | 705
630291101 | 1 | PUMP HOUSE OAK | 64 | 765.4 | 28729.4 | 28729.4 | 2012-06-07 | 2014-03-31 | 2014-03-31 | 110 | LUTKE FOREST PRODS, INC. | 662
630391101 | 1 | OVER THE BRIDGE MIX | 30 | 359.8 | 12090.22 | 1209.02 | 2012-04-16 | 2014-03-31 | 2014-03-31 | 110 | CHRIS PARK | 714
630411201 | 1 | SMORE SALVAGE | 13 | 261 | 6922 | 6922.2 | 2013-03-20 | 2014-03-31 | 2014-03-31 | 110 | DAVID D. HYPES | 376
630551101 | 1 | C110 RACERJACK | 52 | 702.8 | 17499.75 | 1749.98 | 2012-03-20 | 2014-03-31 | 2014-03-31 | 110 | MID MICHIGAN LOGGING | 741
630081101 | 1 | TAILFIN JACK | 79 | 902 | 20203.85 | 2020.39 | 2012-04-03 | 2014-04-01 | 2014-04-01 | 111 | ROTHIG FOREST PRODUCTS, INC. | 728
630211101 | 1 | EVART HARDWOODS | 79 | 1723.6 | 61197 | 6119.7 | 2012-04-25 | 2014-04-01 | 2014-04-01 | 111 | ROBERT OUTMAN | 706
630331101 | 1 | MOTIVATIONAL SANTA OAK | 45 | 948 | 33181.22 | 3318.12 | 2012-03-28 | 2014-04-01 | 2014-04-01 | 111 | MALBURG FOREST PRODUCTS INC | 734
630401001 | 1 | GOPHER RUN | 61 | 1530.8 | 57349.34 | 5734.93 | 2012-03-27 | 2014-04-01 | 2014-04-01 | 111 | LUTKE FOREST PRODS, INC. | 735
630471101 | 1 | GROUSE KABOB JACK | 177 | 2671 | 43879.3 | 4387.93 | 2012-03-26 | 2014-04-01 | 2014-04-01 | 111 | WILL ZOSCSAK | 736
630531101 | 1 | LITTLE OTTER MIX | 56 | 1525.6 | 57246.45 | 57246.45 | 2012-07-10 | 2014-04-01 | 2014-04-01 | 111 | BISBALLE FOREST PRODUCTS | 630
630561101 | 1 | WANDERING EYE RED | 51 | 395 | 21770.78 | 21770.78 | 2012-03-27 | 2014-04-01 | 2014-04-01 | 111 | LUTKE FOREST PRODS, INC. | 735
630571101 | 1 | JUNGLE JACK | 27 | 592.4 | 12320.65 | 1232.07 | 2012-06-29 | 2014-04-01 | 2014-04-01 | 111 | LUTKE FOREST PRODS, INC. | 641
630581101 | 1 | JIMMYS BURNING ASPEN | 123 | 3847.2 | 130164.75 | 130164.75 | 2012-03-13 | 2014-04-01 | 2014-04-01 | 111 | WILLIAM MAEDER | 749
630681101 | 2 | PARANORMAL PINE | 114 | 1936.2 | 89514.73 | 35805.89 | 2012-04-03 | 2014-04-01 | 2014-04-01 | 111 | BIEWER FOREST MANAGEMENT LLC | 728
639111201 | 1 | SHAKEN NOT STIRRED ASPEN | 63 | 1978.6 | 68316.47 | 6831.65 | 2012-04-17 | 2014-04-01 | 2014-04-01 | 111 | DAN BUNDY LOGGING | 714
630021101 | 1 | 131 TRAIL PINES | 199 | 1765.8 | 83153.95 | 8315.4 | 2012-07-10 | 2014-06-30 | 2014-06-30 | 201 | BISBALLE FOREST PRODUCTS | 720
630041101 | 1 | 123 HARDWOODS | 211 | 3395.1 | 270170.83 | 270170.83 | 2012-07-10 | 2014-06-30 | 2014-06-30 | 201 | AJD FOR/PRO | 720
630130801 | 1 | BLUE VALLEY HARDWOODS | 407 | 4058.4 | 111073.2 | 102165.2 | 2009-06-03 | 2012-06-30 | 2014-06-30 | 201 | LOW'S FOREST PRODUCTS | 1853
630150801 | 1 | 10 1/2 HARDWOODS | 179.5 | 2083.6 | 83227.35 | 23779.24 | 2010-04-29 | 2013-06-30 | 2014-06-30 | 201 | LUTKE FOREST PRODS, INC. | 1523
630170801 | 1 | SOUTH 63 HARDWOODS | 225 | 2520.5 | 114430.83 | 16347.26 | 2010-04-29 | 2013-06-30 | 2014-06-30 | 201 | LUTKE FOREST PRODS, INC. | 1523
630201101 | 1 | DOWN THE PATH PINE | 97 | 1733.4 | 130005 | 130005 | 2012-06-11 | 2014-06-30 | 2014-06-30 | 201 | BIEWER FOREST MANAGEMENT LLC | 749
630211001 | 1 | 17+6 RED PINE | 135 | 2310.1 | 202722 | 202722 | 2012-06-11 | 2014-06-30 | 2014-06-30 | 201 | BIEWER FOREST MANAGEMENT LLC | 749
630251101 | 1 | CANNON CREEK MIX | 77 | 1090.3 | 44680.75 | 4468.8 | 2012-05-07 | 2014-06-30 | 2014-06-30 | 201 | CHRIS PARK | 784
630261101 | 1 | GRASS LAKE ASPEN | 22 | 297.4 | 7454.95 | 745.5 | 2012-05-10 | 2014-06-30 | 2014-06-30 | 201 | LUTKE FOREST PRODS, INC. | 781
630290901 | 1 | HOWLING OAK | 143 | 1100.6 | 60121.88 | 60121.88 | 2012-07-10 | 2014-06-30 | 2014-06-30 | 201 | PACKAGING CORP OF AMERICA | 720
630291001 | 1 | MENZIE MIX | 26 | 423.3 | 11986.04 | 1712.3 | 2011-05-20 | 2013-06-30 | 2014-06-30 | 201 | SHAWN MUMA LOGGING | 1137
630301001 | 1 | COON DOOM | 104 | 1824.2 | 36078.93 | 3607.89 | 2011-05-20 | 2014-06-30 | 2014-06-30 | 201 | BISBALLE FOREST PRODUCTS | 1137
630441101 | 1 | GRASS LAKE MIX | 120 | 1101 | 35087.98 | 3508.8 | 2012-07-10 | 2014-06-30 | 2014-06-30 | 201 | C.M. FOREST PRODUCTS, INC. | 720
630461101 | 1 | SCATTERED BIG PINE | 35 | 734.5 | 47391.41 | 14217.42 | 2012-05-21 | 2014-06-30 | 2014-06-30 | 201 | VANDUINEN | 770
630481001 | 1 | CABIN COMBO | 88 | 1618.1 | 45073.12 | 45073.12 | 2011-06-02 | 2013-06-30 | 2014-06-30 | 201 | AJD FOR/PRO | 1124
630501101 | 1 | FLAT TURTLE PINE | 23 | 406.2 | 27091.6 | 8669.31 | 2012-05-10 | 2014-06-30 | 2014-06-30 | 201 | LUTKE FOREST PRODS, INC. | 781
630511101 | 1 | TUCKED SHIRT JACK | 179 | 2256.4 | 44346.5 | 25720.98 | 2012-05-16 | 2014-06-30 | 2014-06-30 | 201 | POTLATCH LAND & LUMBER LLC | 775
630521101 | 1 | RED JACK GREEN ATTACK | 32 | 498.2 | 24544.84 | 2454.48 | 2012-06-08 | 2014-06-30 | 2014-06-30 | 201 | LUTKE FOREST PRODS, INC. | 752
630531001 | 1 | BIG ROCK OAK | 53 | 1109.6 | 43285.68 | 25105.37 | 2012-05-17 | 2014-06-30 | 2014-06-30 | 201 | TD JOHNSON ENTERPRISES LLC | 774
630560901 | 1 | TICK CENTRAL | 42 | 624.3 | 20866.08 | 2980.87 | 1911-06-10 | 2013-06-30 | 2014-06-30 | 201 | VANDUINEN | 37641
630611101 | 1 | BILLY GOAT OAK | 87 | 1425.6 | 54322.7 | 29877.49 | 2012-05-08 | 2014-06-30 | 2014-06-30 | 201 | CHRIS PARK | 783
630631101 | 1 | RUN THROUGH THE JUNGLE ASPEN | 52 | 1192.6 | 43044.3 | 43044.3 | 2012-06-08 | 2014-06-30 | 2014-06-30 | 201 | BISBALLE FOREST PRODUCTS | 752
630641101 | 1 | NEW HOLLAND ASPEN | 42 | 617 | 9723.84 | 9723.84 | 2012-06-18 | 2014-06-30 | 2014-06-30 | 201 | JASON HELSEL | 742
630710901 | 1 | PATCHY OAK | 37 | 904.2 | 25432.29 | 2422.12 | 2011-06-10 | 2011-06-30 | 2014-06-30 | 201 | VANDUINEN | 1116
630250901 | 1 | C23 OAK & PINE | 66 | 1098.2 | 22635.52 | 22635.52 | 2010-05-14 | 2012-06-30 | 2014-07-30 | 231 | DOYLE FOREST PRODUCTS | 1538
630041201 | 1 | 4-SPOT ASPEN | 82 | 1004.8 | 33825.7 | 33825.7 | 2012-09-17 | 2014-09-30 | 2014-09-30 | 293 | C.M. FOREST PRODUCTS, INC. | 743
630051201 | 1 | SOUTHWEST 14 | 55 | 998.8 | 28672.29 | 2867.23 | 2012-11-20 | 2014-09-30 | 2014-09-30 | 293 | GENTZ FOREST PRODUCTS | 679
630061201 | 1 | JACK ON JACK | 162 | 2027.6 | 61074.05 | 6107.41 | 2012-10-22 | 2014-09-30 | 2014-09-30 | 293 | LUTKE FOREST PRODS, INC. | 708
630081201 | 2 | ANYWAY RED PINE | 55 | 502 | 35658.45 | 3565.85 | 2012-09-21 | 2014-09-30 | 2014-09-30 | 293 | BIEWER FOREST MANAGEMENT LLC | 739
630091201 | 1 | WAYBACK MIX | 117 | 2320 | 86047 | 8604.7 | 2012-09-17 | 2014-09-30 | 2014-09-30 | 293 | C.M. FOREST PRODUCTS, INC. | 743
630101201 | 1 | RICKY BOBBY ASPEN | 157 | 2996.6 | 101262.8 | 18227.3 | 2012-10-09 | 2014-09-30 | 2014-09-30 | 293 | CHRIS PARK | 721
630121201 | 1 | JJ RED PINE | 51 | 1130.6 | 87056.2 | 87056.2 | 2012-10-09 | 2014-09-30 | 2014-09-30 | 293 | CHRIS PARK | 721
630161101 | 1 | OIL WELL ASPEN | 206 | 3222.4 | 98291.87 | 56592 | 2011-10-19 | 2013-09-30 | 2014-09-30 | 293 | ROBERT OUTMAN | 1077
630181101 | 1 | ELAN ASPEN/PINE | 60 | 849.8 | 16565.9 | 1656.59 | 2012-08-10 | 2014-09-30 | 2014-09-30 | 293 | SHAWN MUMA LOGGING | 781
630240901 | 1 | BROWSELINE ASPEN | 125 | 2147 | 51523.6 | 5152.36 | 2011-09-16 | 2014-09-30 | 2014-09-30 | 293 | BISBALLE FOREST PRODUCTS | 1110
630271101 | 1 | TOWER RED | 26 | 374.4 | 27994.03 | 8958.09 | 2012-08-14 | 2014-09-30 | 2014-09-30 | 293 | LUTKE FOREST PRODS, INC. | 777
630301101 | 1 | EASTSIDE ASPEN | 69 | 962.6 | 32066.8 | 3206.68 | 2012-08-13 | 2014-09-30 | 2014-09-30 | 293 | BISBALLE FOREST PRODUCTS | 778
630381101 | 1 | PARTY SPOT OAK | 34 | 205 | 7034.45 | 703.45 | 2012-08-14 | 2014-09-30 | 2014-09-30 | 293 | LUTKE FOREST PRODS, INC. | 777
630391001 | 1 | DOLPH PINES | 75 | 1203.9 | 36260.97 | 5180.15 | 2011-09-21 | 2013-09-30 | 2014-09-30 | 293 | SHAWN MUMA LOGGING | 1105
630481101 | 1 | 1/64TH JACK REBORN | 35 | 677.6 | 22402.2 | 2240.22 | 2012-07-24 | 2012-09-30 | 2014-09-30 | 293 | GENTZ FOREST PRODUCTS | 798
630491101 | 1 | AGENT 009 | 112 | 1711.2 | 43607.72 | 4360.77 | 2012-11-20 | 2014-09-30 | 2014-09-30 | 293 | GENTZ FOREST PRODUCTS | 679
630570901 | 1 | KEVINS COMPASS | 41 | 369.8 | 4439.38 | 1715.71 | 2011-04-01 | 2013-09-30 | 2014-09-30 | 293 | BURNS LOGGING | 1278
630671101 | 1 | TREE MONKEY OAK | 14 | 189 | 14899.95 | 1490 | 2012-07-16 | 2014-09-30 | 2014-09-30 | 293 | PACKAGING CORP OF AMERICA | 806
630691101 | 1 | C 25 OAK PUZZLE | 52 | 589.2 | 21881.6 | 2188.16 | 2012-07-24 | 2014-09-30 | 2014-09-30 | 293 | GENTZ FOREST PRODUCTS | 798
630701101 | 1 | GROUSE ON A LOG | 12 | 234 | 3022 | 302.2 | 2012-07-20 | 2014-09-30 | 2014-09-30 | 293 | BUNDY LOGGING, INC. | 802
630011201 | 1 | TEMP BRIDGE SPECIAL | 129 | 1778 | 42787.8 | 4278.78 | 2012-12-10 | 2014-12-31 | 2014-12-31 | 385 | SHAWN MUMA LOGGING | 751
630021201 | 1 | LAZY BOY MIX | 90 | 1624.8 | 28325 | 2832.5 | 2013-01-04 | 2014-12-31 | 2014-12-31 | 385 | WHEELER'S WOLF LAKE SAWMILL | 726
630151201 | 1 | 3 SPOT PINE | 90 | 2328.2 | 141635.4 | 141635.4 | 2013-01-08 | 2014-12-31 | 2014-12-31 | 385 | BIEWER FOREST MANAGEMENT LLC | 722
630191201 | 1 | MUSKY ASPEN | 91 | 1733 | 51293.85 | 41035.08 | 2012-11-14 | 2014-12-31 | 2014-12-31 | 385 | C.M. FOREST PRODUCTS, INC. | 777
630201201 | 1 | 7 MILE MIX | 86 | 1230.3 | 38728.34 | 7745.67 | 2013-01-23 | 2014-12-31 | 2014-12-31 | 385 | MID MICHIGAN LOGGING | 707
630211201 | 1 | 9 MILE MIX | 122 | 2874.6 | 88296.65 | 88296.65 | 2013-01-16 | 2014-12-31 | 2014-12-31 | 385 | BUNDY LOGGING, INC. | 714
630241201 | 1 | HALFWAY BACK | 35 | 880 | 24199.6 | 2419.96 | 2012-12-10 | 2014-12-31 | 2014-12-31 | 385 | SHAWN MUMA LOGGING | 751
630361101 | 1 | WINTER ONLY MIX | 77 | 1047.4 | 20114.03 | 2011.4 | 2012-01-05 | 2014-12-31 | 2014-12-31 | 385 | CHRIS PARK | 1091
630411101 | 1 | SPRUCE GOOSE MIX | 15 | 217 | 2687.35 | 268.74 | 2013-12-09 | 2014-12-31 | 2014-12-31 | 385 | LUTKE FOREST PRODS, INC. | 387
630090901 | 1 | C23 MIX | 271 | 5429.4 | 150007.96 | 45452.42 | 2012-11-07 | 2015-03-30 | 2015-03-30 | 474 | MILLER LOGGING | 873
630031201 | 1 | BALDWIN THREE | 98 | 1509 | 43043.98 | 4304.4 | 2013-03-27 | 2015-03-31 | 2015-03-31 | 475 | GENTZ FOREST PRODUCTS | 734
630091301 | 1 | TAKE 30 PINE | 130 | 483 | 30876.5 | 3087.65 | 2013-04-19 | 2015-03-31 | 2015-03-31 | 475 | BISBALLE FOREST PRODUCTS | 711
630111201 | 1 | MUSKEGON MIX | 25 | 528 | 2499.99 | 250 | 2013-04-10 | 2015-03-31 | 2015-03-31 | 475 | CHRIS PARK | 720
630161201 | 1 | SKI HILL HARDWOODS | 50 | 621.2 | 13365.44 | 13365.44 | 2013-04-09 | 2015-03-31 | 2015-03-31 | 475 | CHRIS PARK | 721
630181201 | 1 | C112 PINE | 115 | 1243.4 | 56249.1 | 5624.91 | 2013-04-19 | 2015-03-31 | 2015-03-31 | 475 | BISBALLE FOREST PRODUCTS | 711
630231201 | 1 | CHADS OAK | 234 | 3386.6 | 111275.68 | 11127.57 | 2013-02-11 | 2015-03-31 | 2015-03-31 | 475 | LUTKE FOREST PRODS, INC. | 778
630251201 | 1 | GROUSES 11 | 57 | 1447.4 | 46165.75 | 28622.68 | 2013-02-20 | 2015-03-31 | 2015-03-31 | 475 | TROY MERRILL | 769
630271201 | 1 | SPITZBERGEN LOGS | 32 | 811 | 28748.35 | 2874.84 | 2013-03-05 | 2015-03-31 | 2015-03-31 | 475 | C.M. FOREST PRODUCTS, INC. | 756
630281201 | 1 | STONEY COMBO | 60 | 1267 | 25348.25 | 3802.23 | 2013-03-05 | 2015-03-31 | 2015-03-31 | 475 | C.M. FOREST PRODUCTS, INC. | 756
630291201 | 1 | C14 SCATTERED OAK | 77 | 1600.8 | 60402.73 | 60402.74 | 2013-04-24 | 2015-03-31 | 2015-03-31 | 475 | NORTHWEST HARDWOODS INC | 706
630311201 | 1 | C14 OAKYPINE | 154 | 2330.3 | 66265.25 | 6626.53 | 2013-07-17 | 2015-03-31 | 2015-03-31 | 475 | GENTZ FOREST PRODUCTS | 622
630341201 | 1 | HORSE APPLES | 99 | 1884.4 | 42408.5 | 4240.85 | 2013-03-27 | 2015-03-31 | 2015-03-31 | 475 | GENTZ FOREST PRODUCTS | 734
630351201 | 1 | PHANTOM MASK | 66 | 1466.2 | 54611.77 | 5461.18 | 2013-02-20 | 2015-03-31 | 2015-03-31 | 475 | TROY MERRILL | 769
630391201 | 1 | SKI HILL JACK | 29 | 229.6 | 5476.75 | 5476.75 | 2013-04-09 | 2015-03-31 | 2015-03-31 | 475 | CHRIS PARK | 721
630421201 | 1 | RED WHITE RED PINE | 88 | 2651 | 160260.32 | 16026.03 | 2013-02-11 | 2015-03-31 | 2015-03-31 | 475 | LUTKE FOREST PRODS, INC. | 778
630451201 | 1 | RPZ | 97 | 3100.4 | 251346.35 | 251346.35 | 2013-04-15 | 2015-03-31 | 2015-03-31 | 475 | BIEWER FOREST MANAGEMENT LLC | 715
630451201 | 2 | RPZ | 97 | 3100.4 | 251346.35 | 251346.35 | 2013-04-15 | 2015-03-31 | 2015-03-31 | 475 | BIEWER FOREST MANAGEMENT LLC | 715
630461201 | 1 | 14 ACRE MIX | 14 | 64 | 1600 | 1600 | 2013-03-20 | 2015-03-31 | 2015-03-31 | 475 | LEWIS DELINE | 741
630471201 | 1 | REC TRAILS MIX | 46 | 738.8 | 21419.2 | 2141.92 | 2013-03-19 | 2015-03-31 | 2015-03-31 | 475 | GENTZ FOREST PRODUCTS | 742
630191101 | 1 | C21 OAK AND ASPEN | 181 | 5902.6 | 207891.37 | 128903.87 | 2012-07-10 | 2015-04-01 | 2015-04-01 | 476 | PACKAGING CORP OF AMERICA | 995
630361201 | 1 | 3 ROCKS AND A SISTA | 45 | 738.1 | 27960.21 | 2796.02 | 2013-05-14 | 2015-04-30 | 2015-04-30 | 505 | DYER'S SAWMILL, INC. | 716
630371201 | 1 | GEEZER OAK | 20 | 371.8 | 12923.95 | 1292.4 | 2013-05-13 | 2015-04-30 | 2015-04-30 | 505 | PACKAGING CORP OF AMERICA | 717
630441201 | 1 | FRANK MIX | 36 | 793.2 | 21065 | 2106.5 | 2013-05-14 | 2015-04-30 | 2015-04-30 | 505 | DYER'S SAWMILL, INC. | 716
630481201 | 1 | FAIR TO MIDDLING MIX | 110 | 1165 | 16024.86 | 1602.49 | 2013-06-04 | 2015-04-30 | 2015-04-30 | 505 | GENTZ FOREST PRODUCTS | 695
630011101 | 1 | PORTER RANCH PINE | 101 | 1769.7 | 32503.02 | 3250.3 | 2012-07-16 | 2015-06-30 | 2015-06-30 | 566 | ROBERT OUTMAN | 1079
630031301 | 1 | RIVERSIDE JACK | 63 | 951.8 | 16213.25 | 1621.33 | 2013-06-07 | 2015-06-30 | 2015-06-30 | 566 | CHRIS PARK | 753
630051301 | 1 | MKS GROUSEY ASPEN | 108 | 1912.8 | 61586.1 | 55427.49 | 2013-06-03 | 2015-06-30 | 2015-06-30 | 566 | DAN BUNDY LOGGING | 757
630061301 | 1 | MKS MIDDLE MIX | 90 | 1694.6 | 51342.9 | 5134.29 | 2013-06-07 | 2015-06-30 | 2015-06-30 | 566 | CHRIS PARK | 753
630071301 | 1 | ACORN ASPEN | 20 | 428 | 11226.65 | 1122.67 | 2013-06-25 | 2015-06-30 | 2015-06-30 | 566 | CHRIS PARK | 735
630101301 | 1 | RED EDMONDS | 38 | 361 | 22417 | 2241.7 | 2013-06-21 | 2015-06-30 | 2015-06-30 | 566 | BISBALLE FOREST PRODUCTS | 739
630121301 | 1 | DUNSMORE CONIFER | 44 | 940 | 101865.2 | 101865.2 | 2013-06-24 | 2015-06-30 | 2015-06-30 | 566 | BIEWER FOREST MANAGEMENT LLC | 736
630451101 | 1 | HAUL ROAD ASPEN | 47 | 689.6 | 14385.36 | 1438.54 | 2012-06-25 | 2015-06-30 | 2015-06-30 | 566 | LUTKE FOREST PRODS, INC. | 1100
630021301 | 1 | 117 HARDWOODS | 396.3 | 4805.4 | 170579.4 | 17057.94 | 2013-12-02 | 2015-09-30 | 2015-09-30 | 658 | CHRIS PARK | 667
630041301 | 1 | 4 MILE HARDWOOD | 36 | 615.6 | 102335.7 | 102335.7 | 2013-09-19 | 2015-09-30 | 2015-09-30 | 658 | POST HARDWOODS, INC. | 741
630191301 | 1 | BIG ASH SALVAGE | 196 | 1267.4 | 22842.4 | 22842.4 | 2013-09-24 | 2015-09-30 | 2015-09-30 | 658 | AJD FOR/PRO | 736
630141301 | 1 | DEER PATCHES | 49 | 1594.8 | 52311.6 | 5231.16 | 2013-08-16 | 2015-10-17 | 2015-10-17 | 675 | HARTER LOGGING | 792
630151301 | 1 | BLASTIN ASPEN | 62 | 2254.2 | 77805.15 | 7780.51 | 2013-08-07 | 2015-10-17 | 2015-10-17 | 675 | LOW'S FOREST PRODUCTS | 801
630161301 | 1 | MEDIUM FINE RED PINE | 28 | 446 | 16510.8 | 1651.08 | 2013-08-12 | 2015-10-17 | 2015-10-17 | 675 | PROCTOR LOGGING | 796
630231301 | 1 | BRIDSON COUNTRY PINE | 49 | 759.8 | 70019.88 | 7001.99 | 2013-11-26 | 2015-12-31 | 2015-12-31 | 750 | POTLATCH LAND & LUMBER LLC | 765
630260901 | 1 | C31 OAK | 196 | 5650 | 227066.92 | 91962.11 | 2012-05-08 | 2014-12-31 | 2015-12-31 | 750 | AJD FOR/PRO | 1332
630271301 | 1 | CRAZY ROBURK HARDWOOD | 125 | 1441.1 | 42141.6 | 4214.16 | 2013-12-02 | 2015-12-31 | 2015-12-31 | 750 | BISBALLE FOREST PRODUCTS | 759
630261201 | 1 | MINIVAN MIX | 75 | 2288.6 | 80113.2 | 8011.32 | 2013-02-05 | 2016-03-31 | 2016-03-31 | 841 | AJD FOR/PRO | 1150