## 
Open Contract Analysis for the Gwinn Forest Management Unit
as of March 10, 2010
Use Page Down Key to See List of Open Sales
Nbr of
|  | Sale Expiration Status | Sales
|  | Contracts Expired | 0 | [9 empty] | Expiration | Expiration | Expiration | Expiration | Expiration
|  | 30 Days before Expiration | 0 | [9 empty] | <0 | >0 | <31 | >30 | <61
|  | 60 Days before Expiration | 0 | [9 empty] | Expiration
|  | >60 Days before Expiration | 109 | [9 empty] | >60
|  | Total | 109
|  | Contract Summary |  |  | Total | [7 empty] | Sale Number | Acres | Volume | Value | Received | Length(days)
|  | Nbr of Open Contracts |  |  | 109 | [7 empty] | > " " | > 0.00 | >0.00 | >0.00 | >0.00 | >0.00
|  | Acres of Open Contracts |  |  | 7009.7
|  | Open Contacts Cords |  |  | 112832.55
|  | Value of Open Contracts |  |  | 3862876.24
|  | Amount Received to Date |  |  | 1599071.92
|  | Amount Remaining |  |  | 2263804.32
|  | Percentage of Contract Value Received to Date |  |  | 41.4%
|  | Expiration Date Used |  |  | 2010-03-10
|  | Avg Contract Length (Years) |  |  | 2.997
Open Timber Sale Contracts sorted by Days Before Expiration
|  |  |  | Total | Current |  | Contract | Original | Current | Days |  | Current
| Cont |  |  | Cord | Contract | Amount | Issue | Expiration | Expiration | Before |  | Contract
Sale Number | Seq | Sale Name | Acres | Volume | Value | Received | Date | Date | Date | Expiration | Purchaser Name | Length(days)
320180701 | 1 | PERRIN CENTRAL SALE | 84.8 | 1859 | 61006.22 | 57345.85 | 2007-09-25 | 2010-05-31 | 2010-05-31 | 82 | JACOBSON LOGGING, INC. | 979
323250601 | 1 | BURMA COUNTRY MIX | 82 | 1253 | 27431.2 | 2743.12 | 2007-07-18 | 2010-05-31 | 2010-05-31 | 82 | GAZAN TIMBER CONTRACTING, INC. | 1048
323220601 | 1 | KAWBAWGAM SALE | 103.1 | 1370.8 | 40371.4 | 4037.14 | 2007-09-21 | 2010-05-31 | 2010-05-31 | 82 | SANVILLE LOGGING, INC. | 983
323190601 | 1 | O'NEIL CREEK SALE | 287.6 | 5198.5 | 158671.5 | 15867.15 | 2007-09-21 | 2010-05-31 | 2010-05-31 | 82 | SANVILLE LOGGING, INC. | 983
321250601 | 1 | YALMER 2 PATCH SALE | 9 | 199.6 | 5966.89 | 1297.15 | 2006-10-05 | 2008-05-31 | 2010-05-31 | 82 | SANVILLE LOGGING, INC. | 1334
320230601 | 1 | TROUT LAKE ROAD PIT SALE | 214.4 | 2224.7 | 100749.01 | 100749.01 | 2007-06-11 | 2010-05-31 | 2010-05-31 | 82 | T-N-T TIMBER PRODUCERS | 1085
323330701 | 2 | FLATROCK SWAMP ROAD SALE | 21.9 | 551 | 7940.1 | 794.01 | 2008-04-11 | 2010-05-31 | 2010-05-31 | 82 | TRIEST FOREST PRODUCTS INC. | 780
320220501 | 1 | CROOKED LAKE ROAD PINE | 70.9 | 1006.2 | 68390.32 | 68390.32 | 2006-07-14 | 2009-05-31 | 2010-05-31 | 82 | LAFLEUR FOREST PRODUCTS | 1417
320270701 | 1 | ALMOST ESKY ASPEN | 15 | 416.3 | 8619.75 | 8619.75 | 2007-10-17 | 2010-05-31 | 2010-05-31 | 82 | KANERVA FOREST PRODUCTS, INC. | 957
321260701 | 2 | DALTON SALE | 23.1 | 258.6 | 7400 | 740 | 2007-11-07 | 2010-05-31 | 2010-05-31 | 82 | TRIEST FOREST PRODUCTS INC. | 936
321240601 | 1 | C4 PATCHES SALE | 42.3 | 881.4 | 26994.45 | 3856.35 | 2006-10-05 | 2009-05-31 | 2010-05-31 | 82 | SANVILLE LOGGING, INC. | 1334
320190601 | 1 | JIMMY'S JAUNT | 53 | 437.8 | 13357.69 | 1335.77 | 2007-06-22 | 2010-05-31 | 2010-05-31 | 82 | GIGUERE LOGGING, INC | 1074
320210701 | 1 | BROKEN HATCHET | 36 | 140 | 8375.04 | 3350.02 | 2007-07-18 | 2010-05-31 | 2010-05-31 | 82 | C.J. LOGGING | 1048
321020601 | 1 | ELF SITE OAK STAND | 57.7 | 943 | 38360 | 38360 | 2006-10-06 | 2009-11-30 | 2010-09-01 | 175 | MINERICK LOGGING, INC | 1426
321040601 | 1 | HELEN LAKE DUMPSTERS SALE | 79.8 | 2359 | 103966.8 | 103966.8 | 2006-10-06 | 2009-11-30 | 2010-09-01 | 175 | MINERICK LOGGING, INC | 1426
321060601 | 1 | HERMIT LAKE GRAVEL PIT | 79.5 | 2316.4 | 71381.3 | 71381.3 | 2007-07-05 | 2009-11-30 | 2010-09-01 | 175 | MINERICK LOGGING, INC | 1154
321120701 | 1 | HIGH-LOW SALE | 62 | 1207 | 32037.75 | 3203.78 | 2007-10-31 | 2010-11-30 | 2010-11-30 | 265 | MINERICK LOGGING, INC | 1126
321140701 | 1 | NORTH FLOPPER SALE | 115.5 | 1939.1 | 56501.42 | 19210.49 | 2007-11-16 | 2010-11-30 | 2010-11-30 | 265 | ROY A. NELSON JR.&SON F.P. INC | 1110
320240501 | 1 | DEER TRAIL BLOCK | 52.1 | 811.2 | 35320.89 | 35320.89 | 2006-07-14 | 2009-11-30 | 2010-11-30 | 265 | LAFLEUR FOREST PRODUCTS | 1600
321110701 | 1 | MOTHER GOOSE MIX | 59 | 1082 | 32082.13 | 3208.21 | 2008-01-03 | 2010-11-30 | 2010-11-30 | 265 | HOLLI FOREST PRODUCTS, INC. | 1062
320340701 | 1 | SQUIRREL HAVEN SALE | 3.2 | 17.64 | 249.92 | 24.99 | 2008-09-04 | 2010-11-30 | 2010-11-30 | 265 | C.J. LOGGING | 817
321080701 | 1 | BOULDER LINE SALE | 23 | 353 | 6917.43 | 6917.43 | 2008-04-07 | 2009-11-30 | 2010-11-30 | 265 | HOLLI FOREST PRODUCTS, INC. | 967
321070701 | 1 | FRANCOEUR PINE SALE | 86.5 | 1701 | 75474.27 | 20378.05 | 2007-09-26 | 2010-11-30 | 2010-11-30 | 265 | HOLLI FOREST PRODUCTS, INC. | 1161
321070601 | 1 | FLOODWOOD SOFTWOOD SALE | 67.3 | 2143 | 82394.65 | 56052.4 | 2007-07-16 | 2010-05-31 | 2010-11-30 | 265 | MINERICK LOGGING, INC | 1233
320300701 | 1 | SMALL JOHNSON CREEK SALE | 3.2 | 27.4 | 614.59 | 61.46 | 2007-09-28 | 2010-11-30 | 2010-11-30 | 265 | C.J. LOGGING | 1159
320110701 | 1 | KNUDSEN ROAD SALE | 24.3 | 300.01 | 10254.37 | 10254.37 | 2007-12-14 | 2010-11-30 | 2010-11-30 | 265 | GAZAN TIMBER CONTRACTING, INC. | 1082
323140701 | 1 | SHOP SALE | 10.5 | 112.8 | 4758.6 | 679.8 | 2007-09-12 | 2009-11-30 | 2010-11-30 | 265 | GAZAN TIMBER CONTRACTING, INC. | 1175
320030601 | 1 | POLE LINE SALE | 16.3 | 280 | 6704.06 | 6704.06 | 2007-08-03 | 2009-11-30 | 2010-11-30 | 265 | VERSO PAPER LLC | 1215
320040601 | 2 | M-35 HARDWOOD | 31.1 | 368.9 | 10439.05 | 6273.86 | 2007-09-12 | 2009-11-30 | 2010-11-30 | 265 | K & K LOGGING | 1175
321300601 | 2 | BRYAN CREEK PINE/BIRCH SALE | 61.1 | 1262 | 37019.38 | 5288.49 | 2007-09-27 | 2009-11-30 | 2010-11-30 | 265 | MINERICK LOGGING, INC | 1160
320100701 | 1 | BACKYARD JACK PINE | 9.4 | 116 | 4622.39 | 462.44 | 2007-12-14 | 2010-11-30 | 2010-11-30 | 265 | KANERVA FOREST PRODUCTS, INC. | 1082
320210201 | 1 | COUNTY LINE MIX | 113.8 | 1324.9 | 50526.16 | 43273.61 | 2005-11-22 | 2008-11-30 | 2010-11-30 | 265 | LAFLEUR FOREST PRODUCTS | 1834
320110801 | 1 | WEST IS BEST | 41 | 618.3 | 21600.13 | 21600.13 | 2008-07-09 | 2010-11-30 | 2010-11-30 | 265 | MINERICK LOGGING, INC | 874
320150701 | 1 | BOB'S LAKE ASPEN/BIRCH | 8.4 | 103.07 | 2861.32 | 286.13 | 2007-12-19 | 2010-11-30 | 2010-11-30 | 265 | C.J. LOGGING | 1077
321200801 | 1 | SHARPTAIL JACK PINE | 34 | 620 | 28685.6 | 2868.56 | 2008-06-10 | 2010-11-30 | 2010-11-30 | 265 | CHOLEWA FOREST PRODUCTS | 903
321160701 | 1 | WHERE'S WARREN | 82 | 1944 | 71776 | 7177.6 | 2007-10-15 | 2010-11-30 | 2010-11-30 | 265 | LAFLEUR FOREST PRODUCTS | 1142
323010901 | 1 | BLACK RIVER FALLS FIRE | 123 | 123 | 2029.5 | 1845 | 2009-08-12 | 2010-01-31 | 2011-03-31 | 386 | J. CAREY LOGGING, INC. | 596
320030801 | 1 | 438 SPLIT | 12 | 59.6 | 1888.94 | 188.89 | 2009-03-26 | 2011-05-30 | 2011-05-30 | 446 | C.J. LOGGING | 795
320100801 | 1 | ESC RIVER MIX | 51 | 665.9 | 18500.44 | 18500.44 | 2009-05-12 | 2011-05-30 | 2011-05-30 | 446 | K & K LOGGING | 748
320250501 | 2 | CR-TWO | 55 | 923.8 | 31157.08 | 31157.08 | 2007-04-16 | 2011-05-31 | 2011-05-31 | 447 | VERSO PAPER LLC | 1506
320260701 | 2 | CHARLIE'S CAMP | 184 | 3890.4 | 125120.6 | 55053.06 | 2007-11-20 | 2011-05-31 | 2011-05-31 | 447 | TRIEST FOREST PRODUCTS INC. | 1288
320140701 | 1 | HAYWIRE HARDWOODS | 178 | 1446.5 | 73462.42 | 7346.24 | 2007-12-14 | 2011-05-31 | 2011-05-31 | 447 | LAFLEUR FOREST PRODUCTS | 1264
320190702 | 1 | SNOWSHOE BLUES | 33 | 711 | 13773.14 | 13773.14 | 2007-12-04 | 2011-05-31 | 2011-05-31 | 447 | GIGUERE LOGGING, INC | 1274
320050801 | 2 | CATS & JAMMERS | 52 | 685 | 18936.2 | 18936.2 | 2008-05-30 | 2011-05-31 | 2011-05-31 | 447 | TRIEST FOREST PRODUCTS INC. | 1096
321020701 | 1 | SAND R. MAPLE SALE | 132.4 | 1944 | 73007.31 | 7300.73 | 2008-04-30 | 2011-05-31 | 2011-05-31 | 447 | ROY A. NELSON JR.&SON F.P. INC | 1126
321030701 | 1 | WOLF LAKE HARDWOOD | 39.3 | 341.4 | 8413.55 | 8413.55 | 2008-03-18 | 2011-05-31 | 2011-05-31 | 447 | S.D. WARREN COMPANY DBA SAPPI | 1169
321040701 | 1 | WOLF TIMBER SALE | 57.5 | 873.8 | 20346.89 | 6917.94 | 2008-06-19 | 2011-05-31 | 2011-05-31 | 447 | HERITAGE TIMBER PRODUCTS | 1076
321160801 | 1 | HEMMINGS LAKE CONGLOMERATE | 51 | 887 | 36012.73 | 3601.27 | 2009-05-13 | 2011-05-31 | 2011-05-31 | 447 | HOLLI FOREST PRODUCTS, INC. | 748
323050801 | 1 | JJ'S GOLD MINE SALE | 48.8 | 437.6 | 13571.4 | 1357.14 | 2009-03-11 | 2011-05-31 | 2011-05-31 | 447 | S.D. WARREN COMPANY DBA SAPPI | 811
323040601 | 2 | NORTH BOAR'S NEST | 184 | 2571.2 | 51680.83 | 21444.7 | 2007-11-21 | 2011-05-31 | 2011-05-31 | 447 | TRIEST FOREST PRODUCTS INC. | 1287
321300801 | 1 | HAWKINS POND ELF TRACKS | 58 | 1165.4 | 45780.4 | 4578.04 | 2009-03-20 | 2011-05-31 | 2011-05-31 | 447 | HOLLI FOREST PRODUCTS, INC. | 802
321290801 | 1 | MT. HARLOW SALE | 60.6 | 889.4 | 34742.88 | 3474.29 | 2009-06-24 | 2011-05-31 | 2011-05-31 | 447 | MINERICK LOGGING | 706
321190801 | 1 | TRASH CAN FIR | 36 | 448 | 10301.7 | 1030.71 | 2008-06-27 | 2011-05-31 | 2011-05-31 | 447 | MINERICK LOGGING, INC | 1068
320080701 | 1 | RT SPECIAL | 59.7 | 1026.4 | 25028.1 | 25028.1 | 2008-01-23 | 2011-11-30 | 2011-11-30 | 630 | GIGUERE LOGGING, INC | 1407
321060901 | 1 | ELF PROJECT ASPEN | 54.6 | 763 | 27962.5 | 2796.25 | 2009-05-19 | 2011-11-30 | 2011-11-30 | 630 | FRANK'S LOGGING | 925
320150801 | 2 | BASIN FIR/HARDWOOD | 55 | 373.15 | 17809.05 | 17809.05 | 2008-05-30 | 2011-11-30 | 2011-11-30 | 630 | TRIEST FOREST PRODUCTS INC. | 1279
321180801 | 1 | MASSED PRODUCTION OAK | 139 | 1695.4 | 38677.25 | 3867.73 | 2009-03-20 | 2011-11-30 | 2011-11-30 | 630 | LAFLEUR FOREST PRODUCTS | 985
321210801 | 1 | TWO STAND JACK SALE | 39 | 552.88 | 20221.25 | 2022.13 | 2008-08-13 | 2011-11-30 | 2011-11-30 | 630 | SANVILLE LOGGING, INC. | 1204
320140801 | 1 | THOMAS CAMP ASPEN | 32 | 558.63 | 16762.04 | 16762.04 | 2008-05-15 | 2011-11-30 | 2011-11-30 | 630 | GIGUERE LOGGING, INC | 1294
321240801 | 1 | MCC SALE | 40 | 815 | 23588.7 | 2358.87 | 2008-11-14 | 2011-11-30 | 2011-11-30 | 630 | LUCAS LOGGING | 1111
320120801 | 1 | PARKER END SALE | 158.3 | 2921.1 | 121437.37 | 78934.29 | 2008-07-28 | 2011-11-30 | 2011-11-30 | 630 | LAFLEUR FOREST PRODUCTS | 1220
321280801 | 1 | DEER CREEK PONDS SALE | 48.6 | 1121 | 41534 | 4153.4 | 2009-06-24 | 2011-11-30 | 2011-11-30 | 630 | MINERICK LOGGING | 889
321060801 | 1 | SLEEMAN POND SALE | 66 | 651.6 | 18079.77 | 1807.98 | 2009-03-20 | 2011-11-30 | 2011-11-30 | 630 | HOLLI FOREST PRODUCTS, INC. | 985
321020801 | 1 | BENTLEY POND SALE | 158 | 3143 | 135526.16 | 13552.62 | 2009-03-20 | 2011-11-30 | 2011-11-30 | 630 | HOLLI FOREST PRODUCTS, INC. | 985
320080801 | 1 | SECTION 32 ROAD ASPEN | 44 | 1021.9 | 35437.34 | 35437.34 | 2009-02-13 | 2011-11-30 | 2011-11-30 | 630 | J. CAREY LOGGING, INC. | 1020
320160801 | 1 | OLD LANDFILL ASPEN | 123.8 | 1949.3 | 72627.08 | 7262.71 | 2008-11-05 | 2011-11-30 | 2011-11-30 | 630 | KANERVA FOREST PRODUCTS, INC. | 1120
320070701 | 1 | SWAMP BUCK HARDWOODS | 59.2 | 670.4 | 16934.4 | 7789.82 | 2007-12-14 | 2011-11-30 | 2011-11-30 | 630 | KANERVA FOREST PRODUCTS, INC. | 1447
320060801 | 1 | BILSKY LAKE ASPEN | 43 | 821.98 | 35053.14 | 3505.31 | 2008-07-21 | 2011-11-30 | 2011-11-30 | 630 | MINERICK LOGGING, INC | 1227
320060701 | 1 | SWAMPBUCK ASPEN | 36 | 859 | 21484.8 | 2148.48 | 2008-03-21 | 2011-11-30 | 2011-11-30 | 630 | SANVILLE LOGGING, INC. | 1349
321050901 | 1 | MURPH'S GRADE MIX | 63.8 | 688.8 | 22315.33 | 2231.53 | 2009-08-12 | 2011-11-30 | 2011-11-30 | 630 | HOLLI FOREST PRODUCTS, INC. | 840
320050701 | 1 | MUD CREEK MIX | 124.5 | 1010.4 | 22584 | 2258.4 | 2008-04-02 | 2011-11-30 | 2011-11-30 | 630 | GIGUERE LOGGING, INC | 1337
321310801 | 1 | MASSED PRODUCTION ASPEN | 84 | 2090 | 73696.58 | 7369.66 | 2009-05-27 | 2011-11-30 | 2011-11-30 | 630 | MINERICK LOGGING, INC | 917
321040801 | 1 | FETCHING YELLOW DOG PINE SALE | 42.4 | 1219 | 49760 | 4976 | 2009-03-20 | 2011-11-30 | 2011-11-30 | 630 | HOLLI FOREST PRODUCTS, INC. | 985
320030701 | 1 | STACK GRADE 07 | 48.8 | 503.8 | 11028.1 | 1102.81 | 2008-03-21 | 2011-11-30 | 2011-11-30 | 630 | SANVILLE LOGGING, INC. | 1349
321040901 | 1 | S-CURVE T-SALE | 33.6 | 495.6 | 13777.5 | 1377.75 | 2009-08-24 | 2011-11-30 | 2011-11-30 | 630 | VERSO PAPER LLC | 828
320010801 | 1 | PBR ASPEN | 108 | 2738.4 | 98683.99 | 98683.99 | 2009-01-21 | 2011-11-30 | 2011-11-30 | 630 | MINERICK LOGGING | 1043
320090801 | 1 | CHANDLER BROOK ASPEN | 43 | 718 | 23687.1 | 2368.71 | 2008-07-09 | 2011-11-30 | 2011-11-30 | 630 | MINERICK LOGGING, INC | 1239
321110901 | 1 | KIDNEY LAKE SALE | 19 | 280 | 5932.3 | 593.23 | 2009-10-21 | 2011-11-30 | 2011-11-30 | 630 | MINERICK LOGGING, INC | 770
321070901 | 1 | PORTERFIELD LAKE SALE | 46.8 | 757.8 | 25549.22 | 2554.92 | 2009-05-04 | 2011-11-30 | 2011-11-30 | 630 | HOLLI FOREST PRODUCTS, INC. | 940
320010701 | 1 | LATHROP SALE | 84.3 | 1388.2 | 32874 | 3287.4 | 2008-01-15 | 2011-11-30 | 2011-11-30 | 630 | GAZAN TIMBER CONTRACTING, INC. | 1415
321080801 | 1 | C. 228 JACK PINE | 20 | 311 | 13236.16 | 1323.62 | 2009-05-04 | 2011-11-30 | 2011-11-30 | 630 | HOLLI FOREST PRODUCTS, INC. | 940
321010801 | 1 | ANDERSON HOMESTEAD SALE | 204 | 3516 | 150825 | 15082.52 | 2009-03-20 | 2011-11-30 | 2011-11-30 | 630 | HOLLI FOREST PRODUCTS, INC. | 985
321080901 | 1 | ELY'S PARK SALE | 12 | 216 | 9284.21 | 928.42 | 2009-08-04 | 2011-11-30 | 2011-11-30 | 630 | HOLLI FOREST PRODUCTS, INC. | 848
321090801 | 1 | T. SALE 109-08 | 15 | 184 | 6460.24 | 646.02 | 2009-03-20 | 2011-11-30 | 2011-11-30 | 630 | HOLLI FOREST PRODUCTS, INC. | 985
321090901 | 1 | TWINN PINES SALE | 99.9 | 2051 | 100691.25 | 10069.13 | 2009-08-12 | 2011-11-30 | 2011-11-30 | 630 | HOLLI FOREST PRODUCTS, INC. | 840
321100801 | 1 | COLD TOES SALE | 63 | 1188 | 37776.99 | 28710.51 | 2008-09-24 | 2011-11-30 | 2011-11-30 | 630 | VERSO PAPER LLC | 1162
321100901 | 1 | WHITE CITY PINE SALE | 43.5 | 1195 | 67075.35 | 67075.35 | 2009-10-21 | 2011-11-30 | 2011-11-30 | 630 | MINERICK LOGGING, INC | 770
321110801 | 1 | BURSTING GROUSE | 41 | 695 | 15100.95 | 15100.95 | 2008-09-15 | 2011-11-30 | 2011-11-30 | 630 | HEIDTMAN LOGGING, INC. | 1171
321050801 | 1 | MIDDLE BRANCH SPLIT SALE | 54.5 | 619.2 | 26442.2 | 2644.22 | 2009-01-22 | 2011-11-30 | 2011-11-30 | 630 | HOLLI FOREST PRODUCTS, INC. | 1042
320210801 | 1 | WERNER BRIDGE SALE | 80.7 | 926.7 | 31716.55 | 3171.66 | 2008-11-05 | 2011-11-30 | 2011-11-30 | 630 | KANERVA FOREST PRODUCTS, INC. | 1120
320190801 | 1 | WATSON INTERSECTION SALE | 83.8 | 859.34 | 28966.16 | 2896.62 | 2008-07-01 | 2011-11-30 | 2011-11-30 | 630 | GIGUERE LOGGING, INC | 1247
320190901 | 1 | GREEN CHAIR ASPEN | 51 | 1155.6 | 33418.92 | 33418.92 | 2009-08-12 | 2011-11-30 | 2011-11-30 | 630 | TRIEST FOREST PRODUCTS INC. | 840
320200801 | 1 | HIGH FENCE ASPEN | 56.2 | 587.56 | 20480.25 | 20480.25 | 2008-08-05 | 2011-11-30 | 2011-11-30 | 630 | DAVE JOHNSON LOGGING | 1212
321150801 | 1 | POT HOLE SALE | 65.5 | 885 | 24753.85 | 2475.39 | 2009-01-21 | 2011-11-30 | 2011-11-30 | 630 | MINERICK LOGGING | 1043
321140801 | 1 | DRAINED POND PINE | 66 | 816.77 | 33826.89 | 3382.69 | 2009-01-22 | 2011-11-30 | 2011-11-30 | 630 | HOLLI FOREST PRODUCTS, INC. | 1042
321150901 | 1 | MULLIGAN CREEK SALE | 15.8 | 258 | 5957.79 | 595.78 | 2010-01-27 | 2011-11-30 | 2011-11-30 | 630 | MINERICK LOGGING, INC | 672
320220801 | 1 | D+D HARDWOODS | 43 | 201.1 | 5923.19 | 592.32 | 2009-03-20 | 2012-05-30 | 2012-05-30 | 812 | ROY A. NELSON JR.&SON F.P. INC | 1167
320210901 | 1 | H. H. PATCHES | 21 | 236.4 | 6396.9 | 639.69 | 2010-01-27 | 2012-05-31 | 2012-05-31 | 813 | ROY A. NELSON JR.&SON F.P. INC | 855
320150901 | 1 | CRACKED CORN | 66 | 1382.9 | 46558.83 | 4655.88 | 2009-08-13 | 2012-05-31 | 2012-05-31 | 813 | MINERICK LOGGING, INC | 1022
321250801 | 1 | CAMP 4 CLUSTER SALE | 55.7 | 1107 | 30247.35 | 30247.35 | 2009-03-06 | 2012-05-31 | 2012-05-31 | 813 | HEIDTMAN LOGGING, INC. | 1182
320220901 | 1 | EAST CABLES MIX | 87 | 1065.4 | 30887.64 | 3088.76 | 2009-03-20 | 2012-05-31 | 2012-05-31 | 813 | LAFLEUR FOREST PRODUCTS | 1168
320200901 | 1 | JERRYS FINAL MARKDOWN SALE | 73.7 | 849.76 | 22727.46 | 2272.75 | 2009-08-13 | 2012-05-31 | 2012-05-31 | 813 | MINERICK LOGGING, INC | 1022
320090901 | 1 | 438 ASPEN | 21 | 430.3 | 13618.4 | 1361.84 | 2009-08-14 | 2012-05-31 | 2012-05-31 | 813 | MINERICK LOGGING, INC | 1021
320020801 | 1 | PBR SOUTH | 50 | 847.7 | 24510.84 | 2451.08 | 2009-05-13 | 2012-05-31 | 2012-05-31 | 813 | J. CAREY LOGGING, INC. | 1114
321030901 | 1 | COUNTY RD. FFH | 41 | 403.8 | 10534.98 | 1053.5 | 2009-08-14 | 2012-05-31 | 2012-05-31 | 813 | MINERICK LOGGING, INC | 1021
320070801 | 1 | TWO COUNTY ASPEN | 70 | 1517.6 | 47941.59 | 4794.16 | 2009-04-01 | 2012-11-30 | 2012-11-30 | 996 | MINERICK LOGGING | 1339
320060901 | 1 | RW HARDWOOD | 14 | 213.4 | 5659.85 | 565.99 | 2009-08-13 | 2012-11-30 | 2012-11-30 | 996 | KANERVA FOREST PRODUCTS, INC. | 1205
321270801 | 1 | SWEENY SAND SALE | 92 | 1958.96 | 48645.96 | 48645.96 | 2008-01-21 | 2012-11-30 | 2012-11-30 | 996 | HEIDTMAN LOGGING, INC. | 1775
321010901 | 1 | MARTIN'S LANDING SALE | 29.6 | 510.7 | 16611.63 | 1661.16 | 2010-01-27 | 2012-11-30 | 2012-11-30 | 996 | MINERICK LOGGING, INC | 1038