## 
Open Contract Analysis for the Cadillac Forest Management Unit
as of May 11, 2005
Use Page Down Key to See List of Open Sales
Nbr of
|  | Sale Expiration Status | Sales
|  | Contracts Expired | 9 | [9 empty] | Expiration | Expiration | Expiration | Expiration | Expiration
|  | 30 Days before Expiration | 0 | [9 empty] | <0 | >0 | <31 | >30 | <61
|  | 60 Days before Expiration | 7 | [9 empty] | Expiration
|  | >60 Days before Expiration | 72 | [9 empty] | >60
|  | Total | 88
|  | Contract Summary |  |  | Total | [7 empty] | Sale Number | Acres | Volume | Value | Received | Length(days)
|  | Nbr of Open Contracts |  |  | 88 | [7 empty] | > " " | > 0.00 | >0.00 | >0.00 | >0.00 | >0.00
|  | Acres of Open Contracts |  |  | 6451.1
|  | Open Contacts Cords |  |  | 105348.38
|  | Value of Open Contracts |  |  | 4734313.48
|  | Amount Received to Date |  |  | 2433099.44
|  | Amount Remaining |  |  | 2301214.04
|  | Percentage of Contract Value Received to Date |  |  | 51.39%
|  | Expiration Date Used |  |  | 2005-05-11
|  | Avg Contract Length (Years) |  |  | 2.4396
Open Timber Sale Contracts sorted by Days Before Expiration
|  |  |  | Total | Current |  | Contract | Original | Current | Days |  | Current
| Cont |  |  | Cord | Contract | Amount | Issue | Expiration | Expiration | Before |  | Contract
Sale Number | Seq | Sale Name | Acres | Volume | Value | Received | Date | Date | Date | Expiration | Purchaser Name | Length(days)
630349702 | 3 | BLIND-FILER CEDAR 1 | 2 | 82.75 | 811.52 | 877.89 | 1997-08-16 | 1998-06-30 | 2003-06-30 | -681 | DARRYL SOPER | 2144
630359702 | 2 | BLIND-FILER CEDAR 2 | 2 | 73 | 536.85 | 565.13 | 1998-12-08 | 2000-12-31 | 2003-06-30 | -681 | DARRYL SOPER | 1665
630620101 | 1 | A & R JACKPINE | 59 | 821.22 | 24680.62 | 24680.56 | 2001-10-11 | 2003-09-30 | 2004-09-30 | -223 | NORTHERN TIMBERLANDS, INC. | 1085
630510101 | 2 | POWER POLE JP | 45 | 728.8 | 22277.1 | 23390.96 | 2001-10-29 | 2003-12-31 | 2004-12-31 | -131 | IB LOGGING | 1159
630850101 | 1 | RAVEN TRAIL | 19 | 163.66 | 3666.5 | 3666.5 | 2001-12-10 | 2003-12-31 | 2004-12-31 | -131 | MICHAEL DELINE | 1117
630390101 | 1 | 123 HARDWOODS | 143 | 1274 | 93450.87 | 93450.87 | 2002-04-19 | 2004-03-31 | 2005-03-31 | -41 | PACKAGING CORP. OF AMERICA | 1077
630300001 | 1 | CABINOAK | 143 | 2884.53 | 122975.6 | 122975.6 | 2001-03-21 | 2003-03-31 | 2005-03-31 | -41 | OUTMAN FOREST PRODUCTS | 1471
630020201 | 1 | SPIKE HARDWOODS | 200 | 1974 | 70458.7 | 70458.7 | 2003-03-11 | 2005-03-31 | 2005-03-31 | -41 | SAPPI/S.D.WARREN COMPANY | 751
630820101 | 1 | WILLY-NILLY HARDWOODS | 83 | 831.66 | 28710.33 | 28710.33 | 2002-05-07 | 2004-03-31 | 2005-03-31 | -41 | NORTHWEST HARDWOODS | 1059
630380201 | 1 | "17 SOUTH PART" | 142 | 1143 | 49341.6 | 49341.6 | 2003-05-20 | 2005-06-30 | 2005-06-30 | 50 | ROBERT GENTZ FOREST PRODUCTS | 772
630440201 | 1 | COMP 14 HARDWOOD | 97 | 1068.4 | 113570.28 | 113570.28 | 2003-05-20 | 2005-06-30 | 2005-06-30 | 50 | ROBERT GENTZ FOREST PRODUCTS | 772
630170201 | 1 | DEAD HORSE BRIDGE JACK PINE | 56 | 745.81 | 20434.5 | 20434.5 | 2003-07-07 | 2005-06-30 | 2005-06-30 | 50 | SHAWN MUMA | 724
630460101 | 1 | HAYMARSH ASPEN | 14 | 285.26 | 10840.72 | 2282.26 | 2001-07-18 | 2003-06-30 | 2005-06-30 | 50 | F.J. FLEES | 1443
630540101 | 1 | NELSON ASPEN | 32 | 372.3 | 11909.12 | 2507.18 | 2001-07-18 | 2003-06-30 | 2005-06-30 | 50 | F.J. FLEES | 1443
630430201 | 1 | RED HAND HARDWOOD | 79 | 1354.2 | 63706.31 | 63706.31 | 2003-05-20 | 2005-06-30 | 2005-06-30 | 50 | DOYLE FOREST PRODUCTS | 772
630100201 | 1 | TRUFFLE PINE | 29 | 250.5 | 19029.05 | 2640.39 | 2002-07-12 | 2004-06-30 | 2005-06-30 | 50 | BLAKE FOREST PRODUCTS | 1084
630250301 | 1 | 87 RP PIECES | 74 | 810.3 | 43933.77 | 4393.38 | 2003-08-25 | 2005-09-30 | 2005-09-30 | 142 | PAYLESS AG PRODUCTS | 767
630050302 | 1 | CON NORTH PINE | 8 | 145.3 | 6538.5 | 6538.5 | 2003-09-17 | 2005-09-30 | 2005-09-30 | 142 | DAN BUNDY LOGGING INC. | 744
630220301 | 1 | COOMBS ASPEN | 65 | 1205 | 55578.33 | 55578.31 | 2003-08-26 | 2005-09-30 | 2005-09-30 | 142 | SAPPI/S.D.WARREN COMPANY | 766
630150201 | 1 | DUSTY PINE | 29 | 349.7 | 10346.23 | 1034.62 | 2002-10-21 | 2005-09-30 | 2005-09-30 | 142 | NORTHERN TIMBERLANDS, INC. | 1075
630200301 | 1 | FIFE LK CRK RP | 38 | 485.3 | 27851.7 | 27851.7 | 2003-08-04 | 2005-09-30 | 2005-09-30 | 142 | PAYLESS AG PRODUCTS | 788
630260301 | 1 | HI-LO ASPEN | 88 | 1906.8 | 81481.4 | 57036.95 | 2003-08-27 | 2005-09-30 | 2005-09-30 | 142 | SHAWN MUMA | 765
630080301 | 1 | HOLEY SAFE | 40 | 900.35 | 33917.6 | 33917.6 | 2003-09-16 | 2005-09-30 | 2005-09-30 | 142 | MURREY FOREST PRODUCTS, INC. | 745
630420201 | 1 | HUNT CLUB SALE | 183 | 4119 | 102039.5 | 102039.5 | 2003-09-17 | 2005-09-30 | 2005-09-30 | 142 | DOYLE FOREST PRODUCTS | 744
630090301 | 1 | SQUIDWARD OAK | 46 | 674.5 | 25111 | 25111 | 2003-09-16 | 2005-09-30 | 2005-09-30 | 142 | MURREY FOREST PRODUCTS, INC. | 745
631000102 | 1 | ANT HARDWOODS | 4 | 33 | 448.3 | 448.3 | 2003-10-21 | 2005-12-30 | 2005-12-30 | 233 | CHANEY CREEK CONSTRUCTION | 801
630350201 | 1 | "ALMOST SLIPPED BY" | 125 | 1714.29 | 78449.78 | 78449.78 | 2003-10-17 | 2005-12-31 | 2005-12-31 | 234 | ROTHIG FOREST PRODUCTS, INC. | 806
630150301 | 1 | ADDMORE HARDWOODS | 212 | 1945.2 | 56916.88 | 56916.88 | 2003-12-09 | 2005-12-31 | 2005-12-31 | 234 | BRUCE BUNDY | 753
630410301 | 1 | BRINKS ASPEN | 53 | 975.88 | 38509.33 | 15403.73 | 2004-01-05 | 2005-12-31 | 2005-12-31 | 234 | SHAWN MUMA | 726
630280301 | 1 | EVART MOREL HARDWOOD | 53 | 2031.6 | 93493.77 | 93493.77 | 2003-10-29 | 2005-12-31 | 2005-12-31 | 234 | BILLSBY LUMBER | 794
630030201 | 1 | JIM DANDY OAK | 165 | 2579.4 | 176916.88 | 176916.88 | 2003-10-24 | 2005-12-31 | 2005-12-31 | 234 | NORTHWEST HARDWOODS | 799
630390301 | 1 | MUSKEGON JACK | 102 | 1009.8 | 34217.01 | 3421.7 | 2004-01-05 | 2005-12-31 | 2005-12-31 | 234 | LUTKE FOREST PRODUCTS | 726
630380301 | 1 | RED ANT JACK | 86 | 805.1 | 31986.62 | 3198.66 | 2004-01-05 | 2005-12-31 | 2005-12-31 | 234 | LUTKE FOREST PRODUCTS | 726
630010201 | 1 | RED DOG HARDWOODS | 203 | 2475.4 | 161461.32 | 80730.66 | 2003-12-09 | 2005-12-31 | 2005-12-31 | 234 | NORTHWEST HARDWOODS | 753
630370301 | 1 | ROLLWAYS RED PINE | 54 | 820.3 | 56534.39 | 5653.44 | 2004-01-12 | 2005-12-31 | 2005-12-31 | 234 | LUTKE FOREST PRODUCTS | 719
630040302 | 1 | WILLIES ASPEN 2 | 64 | 1864.3 | 14975.6 | 4492.68 | 2002-12-10 | 2005-12-31 | 2005-12-31 | 234 | OUTMAN FOREST PRODUCTS | 1117
630500301 | 1 | BEAR BAIT PINE | 33 | 569.2 | 19266.79 | 1926.68 | 2004-02-11 | 2006-03-31 | 2006-03-31 | 324 | BRUCE BUNDY | 779
630300301 | 1 | CYCLE OAK | 35 | 355.3 | 12676.39 | 1267.64 | 2004-04-20 | 2006-03-31 | 2006-03-31 | 324 | ROBERT GENTZ FOREST PRODUCTS | 710
630770101 | 1 | FORGE MIX | 174.3 | 3116 | 164498.98 | 107914.57 | 2002-04-02 | 2005-03-31 | 2006-03-31 | 324 | PAYLESS AG PRODUCTS | 1459
630120201 | 1 | HILLCLIMB VARIETY | 144 | 2100.2 | 71984.4 | 50708.22 | 2003-03-26 | 2005-03-31 | 2006-03-31 | 324 | SHAWN MUMA | 1101
630210101 | 1 | MOREY EAST ASPEN | 92.7 | 2069 | 85232.39 | 11826.5 | 2002-03-21 | 2005-03-31 | 2006-03-31 | 324 | MID MICHIGAN LOGGING | 1471
630230201 | 1 | RIGHT HOOK ASPEN | 31 | 738.1 | 27969.22 | 19673.85 | 2003-03-26 | 2005-03-31 | 2006-03-31 | 324 | SHAWN MUMA | 1101
630360301 | 1 | SEA SHELL SEAT | 30 | 338.69 | 14726.55 | 14726.55 | 2004-04-23 | 2006-03-31 | 2006-03-31 | 324 | PACOLA, DONALD | 707
630480301 | 1 | SKUNKED JACK PINE | 99 | 1348.6 | 36968.72 | 7393.74 | 2004-03-01 | 2006-03-31 | 2006-03-31 | 324 | WEMPLE FOREST PROD-KIMMEL CORP | 760
630340301 | 1 | SQUAWKING BLUEJAY | 18 | 175.55 | 8150.08 | 815.01 | 2004-04-20 | 2006-03-31 | 2006-03-31 | 324 | ROBERT GENTZ FOREST PRODUCTS | 710
630320301 | 1 | WINCH WEDGE | 32 | 428.9 | 18434.5 | 1843.45 | 2004-04-20 | 2006-03-31 | 2006-03-31 | 324 | ROBERT GENTZ FOREST PRODUCTS | 710
630270201 | 1 | DEVIL'S CORNER HDWD | 67 | 1210.5 | 54646.7 | 27323.35 | 2003-05-07 | 2006-06-30 | 2006-06-30 | 415 | MALBURG, RICHARD J. | 1150
630130401 | 1 | ONE TWENTY SIX MIX | 148 | 1795.01 | 55426.58 | 28821.83 | 2004-05-18 | 2006-06-30 | 2006-06-30 | 415 | LUTKE FOREST PRODUCTS | 773
630330401 | 1 | STRATFORD WHITE | 42 | 754.3 | 18926.7 | 1892.67 | 2004-08-05 | 2006-06-30 | 2006-06-30 | 415 | LUTKE FOREST PRODUCTS | 694
630120401 | 1 | X IT ASPEN | 70 | 2664 | 126389.08 | 126389.08 | 2004-06-15 | 2006-06-30 | 2006-06-30 | 415 | SHAWN MUMA | 745
630090401 | 1 | 18 COMBO | 116 | 2675.2 | 121128 | 24225.6 | 2004-09-16 | 2006-09-30 | 2006-09-30 | 507 | MURREY FOREST PRODUCTS, INC. | 744
630180401 | 1 | 2 TIMES RED PINE | 27 | 381 | 21875.25 | 2187.53 | 2004-08-20 | 2006-09-30 | 2006-09-30 | 507 | LUTKE FOREST PRODUCTS | 771
630060201 | 1 | BEUTHIEN ASPEN | 17 | 272.2 | 3255.34 | 325.53 | 2004-08-04 | 2006-09-30 | 2006-09-30 | 507 | LUTKE FOREST PRODUCTS | 787
630450201 | 1 | CAT SCRATCH SPRUCE | 25 | 525.3 | 5056.65 | 505.67 | 2004-08-04 | 2006-09-30 | 2006-09-30 | 507 | LUTKE FOREST PRODUCTS | 787
630010401 | 1 | CENTERLINE GAMBLE | 68 | 1618.76 | 68577.27 | 13715.46 | 2004-08-03 | 2006-09-30 | 2006-09-30 | 507 | ROTHIG FOREST PRODUCTS, INC. | 788
630190401 | 1 | EAST SIDE RED PINE | 61 | 868 | 37652.64 | 3765.26 | 2004-08-20 | 2006-09-30 | 2006-09-30 | 507 | LUTKE FOREST PRODUCTS | 771
630150401 | 1 | FIRST TIMER | 192 | 3838.2 | 108451.44 | 10845.14 | 2004-09-16 | 2006-09-30 | 2006-09-30 | 507 | BISBALLE FOREST PRODUCTS | 744
630140401 | 1 | GOOD OAK | 17 | 271.3 | 10373.94 | 1037.39 | 2004-08-31 | 2006-09-30 | 2006-09-30 | 507 | BRUCE BUNDY | 760
630080401 | 1 | HIGH CENTER | 76 | 1336.16 | 48617.66 | 4861.77 | 2004-08-10 | 2006-09-30 | 2006-09-30 | 507 | DOYLE FOREST PRODUCTS | 781
630430301 | 1 | INDIAN PIPE MIX | 72 | 2708.1 | 200493.89 | 20049.39 | 2004-09-23 | 2006-09-30 | 2006-09-30 | 507 | WEMPLE FOREST PROD-KIMMEL CORP | 737
630110401 | 1 | SATELLITE PINE | 19 | 300.2 | 22671.04 | 2267.1 | 2004-09-23 | 2006-09-30 | 2006-09-30 | 507 | TONY HYDROLAKE LEASING & SERVICE | 737
630940101 | 1 | SPRUCE EDGE | 9 | 157.91 | 1904.88 | 190.49 | 2004-08-05 | 2006-09-30 | 2006-09-30 | 507 | BISBALLE FOREST PRODUCTS | 786
630240401 | 1 | WUOTILA ASPEN | 55 | 1199.5 | 29393.34 | 2939.33 | 2004-07-15 | 2006-09-30 | 2006-09-30 | 507 | MALBURG FOREST PRODUCTS INC | 807
630480401 | 1 | 66-RP | 71 | 873.5 | 68107.17 | 30648.23 | 2005-01-04 | 2006-12-31 | 2006-12-31 | 599 | LUTKE FOREST PRODUCTS | 726
630510401 | 1 | DIXIE PINE | 14 | 128.72 | 11078.2 | 1107.82 | 2005-01-06 | 2006-12-31 | 2006-12-31 | 599 | BISBALLE FOREST PRODUCTS | 724
630450401 | 1 | M-55 MIX | 40 | 600.29 | 16097.44 | 1609.74 | 2005-01-04 | 2006-12-31 | 2006-12-31 | 599 | SHAWN MUMA | 726
630470401 | 1 | MERRIT STONE ASPEN | 36 | 990.37 | 52377.03 | 52377.03 | 2005-01-04 | 2006-12-31 | 2006-12-31 | 599 | SAPPI/SD WARREN SERVICES | 726
630230401 | 1 | TWO-STRIPE PINE | 121 | 1169 | 44869.74 | 4486.97 | 2004-11-15 | 2006-12-31 | 2006-12-31 | 599 | LUTKE FOREST PRODUCTS | 776
630060401 | 1 | BOWMAN REMOVAL | 180 | 2045.9 | 82320.84 | 8232.08 | 2005-03-01 | 2007-03-31 | 2007-03-31 | 689 | SHAWN MUMA | 760
630490401 | 1 | GUARDIAN OAK | 74.1 | 1407.28 | 71970 | 7197 | 2005-02-08 | 2007-03-31 | 2007-03-31 | 689 | ROTHIG FOREST PRODUCTS, INC. | 781
630050401 | 1 | KAL-SAUKEE OAK | 84 | 1226.14 | 61246.66 | 6124.67 | 2005-02-08 | 2007-03-31 | 2007-03-31 | 689 | ROTHIG FOREST PRODUCTS, INC. | 781
630460401 | 1 | LONG HAUL PINE | 222 | 3242.5 | 155121.82 | 15512.18 | 2005-03-28 | 2007-03-31 | 2007-03-31 | 689 | BISBALLE FOREST PRODUCTS | 733
630400401 | 1 | LONG STONEY ASPEN | 20 | 1002.7 | 53965.61 | 5396.56 | 2005-02-22 | 2007-03-31 | 2007-03-31 | 689 | CHRIS MUMA | 767
630200502 | 1 | MODDERS CEDAR 2 | 2 | 55.5 | 444 | 444 | 2005-01-26 | 2007-03-31 | 2007-03-31 | 689 | LOW'S FOREST PRODUCTS | 794
630370401 | 1 | OLD VILLAGE LINE ASPEN | 57 | 1091.4 | 66083.32 | 6608.33 | 2005-03-01 | 2007-03-31 | 2007-03-31 | 689 | SHAWN MUMA | 760
630380401 | 1 | PINELAND ASPEN | 46 | 1051.2 | 64233.6 | 6423.36 | 2005-03-01 | 2007-03-31 | 2007-03-31 | 689 | SAPPI/SD WARREN SERVICES | 760
630240502 | 1 | WALKER RD. CEDAR | 2 | 34.31 | 295.68 | 295.67 | 2005-02-22 | 2007-03-31 | 2007-03-31 | 689 | KARL SCHWENKE | 767
630300401 | 1 | 15 RD. ASPEN | 58 | 1297.9 | 52209.07 | 5220.91 | 2004-10-27 | 2007-06-30 | 2007-06-30 | 780 | SAPPI/SD WARREN SERVICES | 976
630320401 | 1 | DOYLE VOICE ASPEN | 52 | 1948.3 | 92061.52 | 36824.61 | 2004-11-15 | 2007-06-30 | 2007-06-30 | 780 | SHAWN MUMA | 957
630430401 | 1 | FIRETOWER ASPEN | 48 | 1314.2 | 87068.39 | 8706.84 | 2004-11-15 | 2007-06-30 | 2007-06-30 | 780 | MID MICHIGAN LOGGING | 957
630290401 | 1 | GARY'S SOGGY BOOTS | 50 | 825.3 | 26353.76 | 2635.38 | 2005-05-11 | 2007-06-30 | 2007-06-30 | 780 | ROBERT GENTZ FOREST PRODUCTS | 780
630420401 | 1 | HAYFIELD MIX | 115 | 2182.9 | 103345.48 | 33070.55 | 2004-11-15 | 2007-06-30 | 2007-06-30 | 780 | SHAWN MUMA | 957
630070501 | 1 | HIPPO HARDWOODS | 48 | 937.3 | 60192.82 | 30096.41 | 2005-05-06 | 2007-06-30 | 2007-06-30 | 780 | DYER'S SAWMILL, INC. | 785
630540501 | 1 | SMITH'S STRIPS | 104 | 1389.75 | 61416.11 | 6141.61 | 2005-05-02 | 2007-06-30 | 2007-06-30 | 780 | CHRIS MUMA | 789
630520401 | 1 | HILLTOP ASPEN OAK | 194 | 2708.55 | 169278.29 | 169278.29 | 2005-03-11 | 2007-09-30 | 2007-09-30 | 872 | SAPPI/SD WARREN SERVICES | 933
630440401 | 1 | OILFIELD ASPENOAK | 53 | 858.6 | 37892.8 | 37892.8 | 2004-11-15 | 2007-12-31 | 2007-12-31 | 964 | SAPPI/SD WARREN SERVICES | 1141
630410401 | 1 | ROLLING ALLEY OAK | 60 | 754.8 | 39585.63 | 3958.25 | 2005-01-04 | 2007-12-31 | 2007-12-31 | 964 | KAMPS HARDWOODS, INC. | 1091
630080501 | 1 | REEDSBURG CROSSING | 93 | 1493.18 | 74842.5 | 7484.25 | 2005-05-11 | 2008-06-30 | 2008-06-30 | 1146 | SHAWN MUMA | 1146