## 
Open Contract Analysis for the Cadillac Forest Management Unit
as of December 13, 2004
Use Page Down Key to See List of Open Sales
Nbr of
|  | Sale Expiration Status | Sales
|  | Contracts Expired | 6 | [9 empty] | Expiration | Expiration | Expiration | Expiration | Expiration
|  | 30 Days before Expiration | 5 | [9 empty] | <0 | >0 | <31 | >30 | <61
|  | 60 Days before Expiration | 0 | [9 empty] | Expiration
|  | >60 Days before Expiration | 85 | [9 empty] | >60
|  | Total | 96
|  | Contract Summary |  |  | Total | [7 empty] | Sale Number | Acres | Volume | Value | Received | Length(days)
|  | Nbr of Open Contracts |  |  | 96 | [7 empty] | > " " | > 0.00 | >0.00 | >0.00 | >0.00 | >0.00
|  | Acres of Open Contracts |  |  | 6564.5
|  | Open Contacts Cords |  |  | 102579.6
|  | Value of Open Contracts |  |  | 4310627.58
|  | Amount Received to Date |  |  | 2061655.39
|  | Amount Remaining |  |  | 2248972.19
|  | Percentage of Contract Value Received to Date |  |  | 47.83%
|  | Expiration Date Used |  |  | 2004-12-13
|  | Avg Contract Length (Years) |  |  | 2.4127
Open Timber Sale Contracts sorted by Days Before Expiration
|  |  |  | Total | Current |  | Contract | Original | Current | Days |  | Current
| Cont |  |  | Cord | Contract | Amount | Issue | Expiration | Expiration | Before |  | Contract
Sale Number | Seq | Sale Name | Acres | Volume | Value | Received | Date | Date | Date | Expiration | Purchaser Name | Length(days)
630349702 | 3 | BLIND-FILER CEDAR 1 | 2 | 82.75 | 811.52 | 877.89 | 1997-08-16 | 1998-06-30 | 2003-06-30 | -532 | DARRYL SOPER | 2144
630359702 | 2 | BLIND-FILER CEDAR 2 | 2 | 73 | 536.85 | 565.13 | 1998-12-08 | 2000-12-31 | 2003-06-30 | -532 | DARRYL SOPER | 1665
630160101 | 1 | OILFIELD REMOVAL | 54 | 669.8 | 10121.9 | 10121.9 | 2002-02-12 | 2004-03-31 | 2004-03-31 | -257 | SAPPI/S.D.WARREN COMPANY | 778
631100101 | 1 | SPLIT RAIL TRESPASS | 56.6 | 688.4 | 30630.12 | 30630.12 | 2002-05-10 | 2004-03-31 | 2004-03-31 | -257 | DOYLE FOREST PRODUCTS | 691
630140201 | 1 | EACHWAY RED PINE | 58 | 522.49 | 35260.95 | 35260.95 | 2002-07-12 | 2004-06-30 | 2004-06-30 | -166 | DAN BUNDY LOGGING INC. | 719
630620101 | 1 | A & R JACKPINE | 59 | 821.22 | 24680.62 | 24680.56 | 2001-10-11 | 2003-09-30 | 2004-09-30 | -74 | NORTHERN TIMBERLANDS | 1085
630900102 | 1 | BORN AGAIN ASPEN | 36 | 682.37 | 4417.2 | 4417.2 | 2001-12-17 | 2004-12-31 | 2004-12-31 | 18 | PARK, CHRIS | 1110
630510101 | 2 | POWER POLE JP | 45 | 728.8 | 22277.1 | 23390.96 | 2001-10-29 | 2003-12-31 | 2004-12-31 | 18 | IB LOGGING | 1159
630840101 | 1 | Q-TIP RED PINE | 36 | 325.15 | 22658.66 | 22658.66 | 2001-11-20 | 2003-12-31 | 2004-12-31 | 18 | NORTHERN TIMBERLANDS | 1137
630850101 | 1 | RAVEN TRAIL | 19 | 163.66 | 3666.5 | 3666.5 | 2001-12-10 | 2003-12-31 | 2004-12-31 | 18 | MICHAEL DELINE | 1117
630910102 | 1 | WEST BRANCH ASPEN | 70 | 835.51 | 5595.3 | 5595.3 | 2001-12-12 | 2004-12-31 | 2004-12-31 | 18 | PARK, CHRIS | 1115
630390101 | 1 | 123 HARDWOODS | 143 | 1274 | 93450.87 | 93450.87 | 2002-04-19 | 2004-03-31 | 2005-03-31 | 108 | PACKAGING CORP. OF AMERICA | 1077
630290201 | 2 | BLACKMAIL PINE & OAK | 63 | 964.2 | 31935.02 | 31935.02 | 2002-10-09 | 2004-09-30 | 2005-03-31 | 108 | MALBURG FOREST PRODUCTS INC | 904
630300001 | 1 | CABINOAK | 143 | 2884.53 | 122975.6 | 100842.03 | 2001-03-21 | 2003-03-31 | 2005-03-31 | 108 | OUTMAN FOREST PRODUCTS | 1471
630030301 | 1 | DUNSMORE SALVAGE | 17 | 42.5 | 765.43 | 76.54 | 2003-01-09 | 2005-03-31 | 2005-03-31 | 108 | GARY DOVE | 812
630010301 | 1 | DYER SALVAGE | 5 | 26 | 391.3 | 391.3 | 2003-01-09 | 2005-03-31 | 2005-03-31 | 108 | GARY DOVE | 812
630770101 | 1 | FORGE MIX | 174.3 | 3116 | 161669.76 | 16166.98 | 2002-04-02 | 2005-03-31 | 2005-03-31 | 108 | PAYLESS AG PRODUCTS | 1094
630120201 | 1 | HILLCLIMB VARIETY | 144 | 2100.2 | 70920.59 | 7092.06 | 2003-03-26 | 2005-03-31 | 2005-03-31 | 108 | SHAWN MUMA | 736
630330101 | 1 | HORSE TROUGH OAK | 142 | 1735.7 | 53756.36 | 45752.94 | 2002-02-12 | 2004-03-31 | 2005-03-31 | 108 | DAN BUNDY LOGGING INC. | 1143
630210101 | 1 | MOREY EAST ASPEN | 92.7 | 2069 | 81562.1 | 8156.21 | 2002-03-21 | 2005-03-31 | 2005-03-31 | 108 | MID MICHIGAN LOGGING | 1106
630230201 | 1 | RIGHT HOOK ASPEN | 31 | 738.1 | 27651.23 | 2765.12 | 2003-03-26 | 2005-03-31 | 2005-03-31 | 108 | SHAWN MUMA | 736
630300101 | 1 | ROLLING RED | 199 | 2029.5 | 57131.13 | 57131.13 | 2002-02-08 | 2004-03-31 | 2005-03-31 | 108 | ROBERT GENTZ FOREST PRODUCTS | 1147
630020201 | 1 | SPIKE HARDWOODS | 200 | 1974 | 70458.7 | 70458.7 | 2003-03-11 | 2005-03-31 | 2005-03-31 | 108 | SAPPI/S.D.WARREN COMPANY | 751
630820101 | 1 | WILLY-NILLY HARDWOODS | 83 | 831.66 | 28710.33 | 28710.33 | 2002-05-07 | 2004-03-31 | 2005-03-31 | 108 | NORTHWEST HARDWOODS | 1059
630380201 | 1 | "17 SOUTH PART" | 142 | 1143 | 49341.6 | 49341.6 | 2003-05-20 | 2005-06-30 | 2005-06-30 | 199 | ROBERT GENTZ FOREST PRODUCTS | 772
630250201 | 1 | 23 ROAD MIX | 26 | 274.5 | 11892.77 | 1650.19 | 2002-08-02 | 2004-06-30 | 2005-06-30 | 199 | BRUCE BUNDY | 1063
630440201 | 1 | COMP 14 HARDWOOD | 97 | 1068.4 | 113570.28 | 113570.28 | 2003-05-20 | 2005-06-30 | 2005-06-30 | 199 | ROBERT GENTZ FOREST PRODUCTS | 772
630170201 | 1 | DEAD HORSE BRIDGE JACK PINE | 56 | 745.81 | 20434.5 | 2043.45 | 2003-07-07 | 2005-06-30 | 2005-06-30 | 199 | SHAWN MUMA | 724
630460101 | 1 | HAYMARSH ASPEN | 14 | 285.26 | 10840.72 | 2282.26 | 2001-07-18 | 2003-06-30 | 2005-06-30 | 199 | F.J. FLEES | 1443
630240201 | 1 | HOPPING HUMMOCKS MIX | 78 | 642 | 18778.25 | 1877.83 | 2003-07-07 | 2005-06-30 | 2005-06-30 | 199 | SHAWN MUMA | 724
630540101 | 1 | NELSON ASPEN | 32 | 372.3 | 11909.12 | 2507.18 | 2001-07-18 | 2003-06-30 | 2005-06-30 | 199 | F.J. FLEES | 1443
630430201 | 1 | RED HAND HARDWOOD | 79 | 1354.2 | 63706.31 | 63706.31 | 2003-05-20 | 2005-06-30 | 2005-06-30 | 199 | DOYLE FOREST PRODUCTS | 772
630160201 | 1 | SEVEN POINT ASPEN | 52.4 | 624.6 | 21594.7 | 2159.47 | 2003-07-07 | 2005-06-30 | 2005-06-30 | 199 | SHAWN MUMA | 724
630410201 | 1 | STACKPOLE RED PINE | 32.5 | 294.8 | 10236.5 | 1023.65 | 2003-07-02 | 2005-06-30 | 2005-06-30 | 199 | LEON CORLEW | 729
630100201 | 1 | TRUFFLE PINE | 29 | 250.5 | 19029.05 | 2640.39 | 2002-07-12 | 2004-06-30 | 2005-06-30 | 199 | BLAKE FOREST PRODUCTS | 1084
630240301 | 1 | 7 MILE WP | 27 | 293.6 | 8120.59 | 812.06 | 2003-08-07 | 2005-09-30 | 2005-09-30 | 291 | BRUCE BUNDY | 785
630250301 | 1 | 87 RP PIECES | 74 | 810.3 | 43933.77 | 4393.38 | 2003-08-25 | 2005-09-30 | 2005-09-30 | 291 | PAYLESS AG PRODUCTS | 767
630050302 | 1 | CON NORTH PINE | 8 | 145.3 | 6538.5 | 6538.5 | 2003-09-17 | 2005-09-30 | 2005-09-30 | 291 | DAN BUNDY LOGGING INC. | 744
630220301 | 1 | COOMBS ASPEN | 65 | 1205 | 55578.33 | 55578.31 | 2003-08-26 | 2005-09-30 | 2005-09-30 | 291 | SAPPI/S.D.WARREN COMPANY | 766
630150201 | 1 | DUSTY PINE | 29 | 349.7 | 10346.23 | 1034.62 | 2002-10-21 | 2005-09-30 | 2005-09-30 | 291 | NORTHERN TIMBERLANDS | 1075
630200301 | 1 | FIFE LK CRK RP | 38 | 485.3 | 27016.65 | 2701.67 | 2003-08-04 | 2005-09-30 | 2005-09-30 | 291 | PAYLESS AG PRODUCTS | 788
630260301 | 1 | HI-LO ASPEN | 88 | 1906.8 | 81481.4 | 57036.95 | 2003-08-27 | 2005-09-30 | 2005-09-30 | 291 | SHAWN MUMA | 765
630080301 | 1 | HOLEY SAFE | 40 | 900.35 | 33917.6 | 3391.76 | 2003-09-16 | 2005-09-30 | 2005-09-30 | 291 | MURREY FOREST PRODUCTS, INC. | 745
630420201 | 1 | HUNT CLUB SALE | 183 | 4119 | 101639.5 | 25409.88 | 2003-09-17 | 2005-09-30 | 2005-09-30 | 291 | DOYLE FOREST PRODUCTS | 744
630230301 | 1 | RXB PINE | 85 | 1172.1 | 54053.29 | 5405.33 | 2003-08-07 | 2005-09-30 | 2005-09-30 | 291 | BRUCE BUNDY | 785
630090301 | 1 | SQUIDWARD OAK | 46 | 674.5 | 25111 | 25111 | 2003-09-16 | 2005-09-30 | 2005-09-30 | 291 | MURREY FOREST PRODUCTS, INC. | 745
631000102 | 1 | ANT HARDWOODS | 4 | 33 | 448.3 | 448.3 | 2003-10-21 | 2005-12-30 | 2005-12-30 | 382 | CHANEY CREEK CONSTRUCTION | 801
630350201 | 1 | "ALMOST SLIPPED BY" | 125 | 1714.29 | 78449.78 | 78449.78 | 2003-10-17 | 2005-12-31 | 2005-12-31 | 383 | ROTHIG FOREST PRODUCTS, INC. | 806
630150301 | 1 | ADDMORE HARDWOODS | 212 | 1945.2 | 56916.88 | 45533.5 | 2003-12-09 | 2005-12-31 | 2005-12-31 | 383 | BRUCE BUNDY | 753
630350301 | 1 | BEE NIMBLE JACK | 117 | 1499.9 | 43203.47 | 43203.47 | 2003-11-26 | 2005-12-31 | 2005-12-31 | 383 | LUTKE FOREST PRODUCTS INC | 766
630410301 | 1 | BRINKS ASPEN | 53 | 975.88 | 38509.33 | 15403.73 | 2004-01-05 | 2005-12-31 | 2005-12-31 | 383 | SHAWN MUMA | 726
630280301 | 1 | EVART MOREL HARDWOOD | 53 | 2031.6 | 93493.74 | 56096.28 | 2003-10-29 | 2005-12-31 | 2005-12-31 | 383 | BILLSBY LUMBER | 794
630030201 | 1 | JIM DANDY OAK | 165 | 2579.4 | 176916.88 | 176916.88 | 2003-10-24 | 2005-12-31 | 2005-12-31 | 383 | NORTHWEST HARDWOODS | 799
630390301 | 1 | MUSKEGON JACK | 102 | 1009.8 | 34217.01 | 3421.7 | 2004-01-05 | 2005-12-31 | 2005-12-31 | 383 | LUTKE FOREST PRODUCTS INC | 726
630380301 | 1 | RED ANT JACK | 86 | 805.1 | 31986.62 | 3198.66 | 2004-01-05 | 2005-12-31 | 2005-12-31 | 383 | LUTKE FOREST PRODUCTS INC | 726
630010201 | 1 | RED DOG HARDWOODS | 203 | 2475.4 | 161461.32 | 80730.66 | 2003-12-09 | 2005-12-31 | 2005-12-31 | 383 | NORTHWEST HARDWOODS | 753
630370301 | 1 | ROLLWAYS RED PINE | 54 | 820.3 | 56534.39 | 5653.44 | 2004-01-12 | 2005-12-31 | 2005-12-31 | 383 | LUTKE FOREST PRODUCTS INC | 719
630040302 | 1 | WILLIES ASPEN 2 | 64 | 1864.3 | 14975.6 | 4492.68 | 2002-12-10 | 2005-12-31 | 2005-12-31 | 383 | OUTMAN FOREST PRODUCTS | 1117
630500301 | 1 | BEAR BAIT PINE | 33 | 569.2 | 19266.79 | 1926.68 | 2004-02-11 | 2006-03-31 | 2006-03-31 | 473 | BRUCE BUNDY | 779
630300301 | 1 | CYCLE OAK | 35 | 355.3 | 12676.39 | 1267.64 | 2004-04-20 | 2006-03-31 | 2006-03-31 | 473 | ROBERT GENTZ FOREST PRODUCTS | 710
630030401 | 1 | LONG ARM OAK | 17 | 250.7 | 6545.64 | 654.56 | 2004-04-20 | 2006-03-31 | 2006-03-31 | 473 | S.D.WARREN SERVICES CO | 710
630470301 | 1 | POTHOLE PINE | 68 | 903.9 | 31179.31 | 3117.93 | 2004-02-11 | 2006-03-31 | 2006-03-31 | 473 | BRUCE BUNDY | 779
630020401 | 1 | SCHNAUZER HARDWOODS | 82 | 1049.7 | 78783.17 | 78783.17 | 2004-03-29 | 2006-03-31 | 2006-03-31 | 473 | BFP MANAGEMENT, INC. | 732
630360301 | 1 | SEA SHELL SEAT | 30 | 338.69 | 14726.55 | 1472.66 | 2004-04-23 | 2006-03-31 | 2006-03-31 | 473 | PACOLA, DONALD | 707
630480301 | 1 | SKUNKED JACK PINE | 99 | 1348.6 | 36968.72 | 7393.74 | 2004-03-01 | 2006-03-31 | 2006-03-31 | 473 | WEMPLE FOREST PRODUCTS | 760
630340301 | 1 | SQUAWKING BLUEJAY | 18 | 175.55 | 8150.08 | 815.01 | 2004-04-20 | 2006-03-31 | 2006-03-31 | 473 | ROBERT GENTZ FOREST PRODUCTS | 710
630320301 | 1 | WINCH WEDGE | 32 | 428.9 | 18434.5 | 1843.45 | 2004-04-20 | 2006-03-31 | 2006-03-31 | 473 | ROBERT GENTZ FOREST PRODUCTS | 710
630270201 | 1 | DEVIL'S CORNER HDWD | 67 | 1210.5 | 54646.7 | 27323.35 | 2003-05-07 | 2006-06-30 | 2006-06-30 | 564 | MALBURG, RICHARD J. | 1150
630130401 | 1 | ONE TWENTY SIX MIX | 148 | 1795.01 | 55426.58 | 16073.71 | 2004-05-18 | 2006-06-30 | 2006-06-30 | 564 | LUTKE FOREST PRODUCTS INC | 773
630070401 | 1 | POWERLINE OAK | 26 | 327.36 | 10487.9 | 1048.79 | 2004-05-25 | 2006-06-30 | 2006-06-30 | 564 | DYERS SAWMILL INC | 766
630330401 | 1 | STRATFORD WHITE | 42 | 754.3 | 18926.7 | 1892.67 | 2004-08-05 | 2006-06-30 | 2006-06-30 | 564 | LUTKE FOREST PRODUCTS INC | 694
630120401 | 1 | X IT ASPEN | 70 | 2664 | 126389.08 | 126389.08 | 2004-06-15 | 2006-06-30 | 2006-06-30 | 564 | SHAWN MUMA | 745
630090401 | 1 | 18 COMBO | 116 | 2675.2 | 121128 | 12112.8 | 2004-09-16 | 2006-09-30 | 2006-09-30 | 656 | MURREY FOREST PRODUCTS, INC. | 744
630180401 | 1 | 2 TIMES RED PINE | 27 | 381 | 21875.25 | 2187.53 | 2004-08-20 | 2006-09-30 | 2006-09-30 | 656 | LUTKE FOREST PRODUCTS INC | 771
630170401 | 1 | 64 RED PINE | 31 | 494.9 | 36280.33 | 36280.33 | 2004-08-30 | 2006-09-30 | 2006-09-30 | 656 | BIEWER SAWMILL INC | 761
630060201 | 1 | BEUTHIEN ASPEN | 17 | 272.2 | 3255.34 | 325.53 | 2004-08-04 | 2006-09-30 | 2006-09-30 | 656 | LUTKE FOREST PRODUCTS INC | 787
630450201 | 1 | CAT SCRATCH SPRUCE | 25 | 525.3 | 5056.65 | 505.67 | 2004-08-04 | 2006-09-30 | 2006-09-30 | 656 | LUTKE FOREST PRODUCTS INC | 787
630010401 | 1 | CENTERLINE GAMBLE | 68 | 1618.76 | 68577.27 | 6857.73 | 2004-08-03 | 2006-09-30 | 2006-09-30 | 656 | ROTHIG FOREST PRODUCTS, INC. | 788
630190401 | 1 | EAST SIDE RED PINE | 61 | 868 | 37652.64 | 3765.26 | 2004-08-20 | 2006-09-30 | 2006-09-30 | 656 | LUTKE FOREST PRODUCTS INC | 771
630150401 | 1 | FIRST TIMER | 192 | 3838.2 | 108451.44 | 10845.14 | 2004-09-16 | 2006-09-30 | 2006-09-30 | 656 | KURT BISBALLE | 744
630140401 | 1 | GOOD OAK | 17 | 271.3 | 10373.94 | 1037.39 | 2004-08-31 | 2006-09-30 | 2006-09-30 | 656 | BRUCE BUNDY | 760
630200401 | 1 | HARVEYS ASPEN | 46 | 925.3 | 58550.67 | 5855.06 | 2004-07-25 | 2006-09-30 | 2006-09-30 | 656 | S.D.WARREN SERVICES CO | 797
630080401 | 1 | HIGH CENTER | 76 | 1336.16 | 48617.66 | 4861.77 | 2004-08-10 | 2006-09-30 | 2006-09-30 | 656 | DOYLE FOREST PRODUCTS | 781
630430301 | 1 | INDIAN PIPE MIX | 72 | 2708.1 | 200493.89 | 20049.39 | 2004-09-23 | 2006-09-30 | 2006-09-30 | 656 | WEMPLE FOREST PRODUCTS | 737
630250401 | 1 | LONG STONEY RED | 25 | 453.39 | 33083.7 | 3308.37 | 2004-09-14 | 2006-09-30 | 2006-09-30 | 656 | BIEWER SAWMILL INC | 746
630270401 | 1 | ROTTEN ROTTWEILER ASPEN | 26 | 425.94 | 12367.8 | 1236.78 | 2004-08-31 | 2006-09-30 | 2006-09-30 | 656 | BRUCE BUNDY | 760
630110401 | 1 | SATELLITE PINE | 19 | 300.2 | 22671.04 | 2267.1 | 2004-09-23 | 2006-09-30 | 2006-09-30 | 656 | TONY HYDROLAKE LEASING & SERVICE | 737
630940101 | 1 | SPRUCE EDGE | 9 | 157.91 | 1904.88 | 190.49 | 2004-08-05 | 2006-09-30 | 2006-09-30 | 656 | KURT BISBALLE | 786
630240401 | 1 | WUOTILA ASPEN | 55 | 1199.5 | 29393.34 | 2939.33 | 2004-07-15 | 2006-09-30 | 2006-09-30 | 656 | MALBURG FOREST PRODUCTS INC | 807
630230401 | 1 | TWO-STRIPE PINE | 121 | 1169 | 44869.74 | 4486.97 | 2004-11-15 | 2006-12-31 | 2006-12-31 | 748 | LUTKE FOREST PRODUCTS INC | 776
630300401 | 1 | 15 RD. ASPEN | 58 | 1297.9 | 52209.07 | 5220.91 | 2004-10-27 | 2007-06-30 | 2007-06-30 | 929 | S.D.WARREN SERVICES CO | 976
630320401 | 1 | DOYLE VOICE ASPEN | 52 | 1948.3 | 92061.52 | 9206.15 | 2004-11-15 | 2007-06-30 | 2007-06-30 | 929 | SHAWN MUMA | 957
630430401 | 1 | FIRETOWER ASPEN | 48 | 1314.2 | 87068.39 | 8706.84 | 2004-11-15 | 2007-06-30 | 2007-06-30 | 929 | MID MICHIGAN LOGGING | 957
630420401 | 1 | HAYFIELD MIX | 115 | 2182.9 | 103345.48 | 10334.55 | 2004-11-15 | 2007-06-30 | 2007-06-30 | 929 | SHAWN MUMA | 957
630260401 | 1 | M-37 ASPEN | 35 | 935.6 | 32619.51 | 32619.51 | 2004-10-27 | 2007-06-30 | 2007-06-30 | 929 | S.D.WARREN SERVICES CO | 976
630440401 | 1 | OILFIELD ASPENOAK | 53 | 858.6 | 37892.8 | 37892.8 | 2004-11-15 | 2007-12-31 | 2007-12-31 | 1113 | S.D.WARREN SERVICES CO | 1141