## 
Open Contract Analysis for the Gwinn Forest Management Unit
as of May 13, 2009
Use Page Down Key to See List of Open Sales
Nbr of
|  | Sale Expiration Status | Sales
|  | Contracts Expired | 0 | [9 empty] | Expiration | Expiration | Expiration | Expiration | Expiration
|  | 30 Days before Expiration | 6 | [9 empty] | <0 | >0 | <31 | >30 | <61
|  | 60 Days before Expiration | 0 | [9 empty] | Expiration
|  | >60 Days before Expiration | 120 | [9 empty] | >60
|  | Total | 126
|  | Contract Summary |  |  | Total | [7 empty] | Sale Number | Acres | Volume | Value | Received | Length(days)
|  | Nbr of Open Contracts |  |  | 126 | [7 empty] | > " " | > 0.00 | >0.00 | >0.00 | >0.00 | >0.00
|  | Acres of Open Contracts |  |  | 8179.4
|  | Open Contacts Cords |  |  | 126402.45
|  | Value of Open Contracts |  |  | 4412456.83
|  | Amount Received to Date |  |  | 1152292.91
|  | Amount Remaining |  |  | 3260163.92
|  | Percentage of Contract Value Received to Date |  |  | 26.11%
|  | Expiration Date Used |  |  | 2009-05-13
|  | Avg Contract Length (Years) |  |  | 2.9648
Open Timber Sale Contracts sorted by Days Before Expiration
|  |  |  | Total | Current |  | Contract | Original | Current | Days |  | Current
| Cont |  |  | Cord | Contract | Amount | Issue | Expiration | Expiration | Before |  | Contract
Sale Number | Seq | Sale Name | Acres | Volume | Value | Received | Date | Date | Date | Expiration | Purchaser Name | Length(days)
321240601 | 1 | C4 PATCHES SALE | 42.3 | 881.4 | 25709 | 2570.9 | 2006-10-05 | 2009-05-31 | 2009-05-31 | 18 | SANVILLE LOGGING, INC. | 969
323230601 | 1 | COUNTY LINE SALE | 72 | 273.4 | 4071 | 4071 | 2007-11-20 | 2009-05-31 | 2009-05-31 | 18 | ASPEN LUMBER CO. | 558
321250601 | 1 | YALMER 2 PATCH SALE | 9 | 199.6 | 5448.03 | 778.29 | 2006-10-05 | 2008-05-31 | 2009-05-31 | 18 | SANVILLE LOGGING, INC. | 969
320220501 | 1 | CROOKED LAKE ROAD PINE | 70.9 | 1006.2 | 68390.32 | 6839.03 | 2006-07-14 | 2009-05-31 | 2009-05-31 | 18 | LAFLEUR FOREST PRODUCTS | 1052
320020501 | 1 | PERRIN BROS HARDWOOD | 131 | 1457.4 | 72313.99 | 33987.58 | 2006-07-14 | 2009-05-31 | 2009-05-31 | 18 | LAFLEUR FOREST PRODUCTS | 1052
320320401 | 1 | DAN'S DETOUR | 330 | 3278.5 | 172471.61 | 172471.61 | 2005-06-27 | 2008-05-31 | 2009-05-31 | 18 | S.D. WARREN COMPANY DBA SAPPI | 1434
321080701 | 1 | BOULDER LINE SALE | 23 | 353 | 6588.03 | 658.8 | 2008-04-07 | 2009-11-30 | 2009-11-30 | 201 | HOLLI FOREST PRODUCTS, INC. | 602
320140601 | 1 | LEIGHTON ROAD SALE | 15.2 | 371.6 | 14812.52 | 1481.25 | 2007-06-22 | 2009-11-30 | 2009-11-30 | 201 | GIGUERE LOGGING, INC | 892
320240501 | 1 | DEER TRAIL BLOCK | 52.1 | 811.2 | 34645.31 | 21133.64 | 2006-07-14 | 2009-11-30 | 2009-11-30 | 201 | LAFLEUR FOREST PRODUCTS | 1235
320110601 | 1 | CAMP 8 CREEK ASPEN | 28.1 | 529.25 | 17860.24 | 1786.02 | 2006-09-21 | 2009-11-30 | 2009-11-30 | 201 | MINERICK LOGGING, INC | 1166
320210601 | 1 | PAULSEN ROAD HARDWOOD SALE | 16.5 | 90 | 6590.88 | 659.09 | 2007-05-29 | 2009-11-30 | 2009-11-30 | 201 | KANERVA FOREST PRODUCTS, INC. | 916
320100601 | 1 | FRANCIS HARDWOOD | 60 | 560.3 | 24230.61 | 2423.06 | 2007-06-15 | 2009-11-30 | 2009-11-30 | 201 | ST. JOHN FOREST PRODUCTS, INC. | 899
321020601 | 1 | ELF SITE OAK STAND | 57.7 | 943 | 38360 | 38360 | 2006-10-06 | 2009-11-30 | 2009-11-30 | 201 | MINERICK LOGGING, INC | 1151
321200601 | 1 | 480 ASPEN SALE | 36.1 | 792 | 32333.37 | 32333.37 | 2007-07-25 | 2009-11-30 | 2009-11-30 | 201 | JACOBSON LOGGING, INC. | 859
320210201 | 1 | COUNTY LINE MIX | 113.8 | 1324.9 | 50526.16 | 7010.79 | 2005-11-22 | 2008-11-30 | 2009-11-30 | 201 | LAFLEUR FOREST PRODUCTS | 1469
320180501 | 1 | 565 ASPEN | 108.9 | 2232.67 | 93764 | 63759.52 | 2006-08-23 | 2009-11-30 | 2009-11-30 | 201 | LAFLEUR FOREST PRODUCTS | 1195
320200501 | 1 | BEAR CREEK BIRCH | 48.6 | 1038.77 | 46932.61 | 4693.26 | 2006-08-22 | 2009-11-30 | 2009-11-30 | 201 | LAFLEUR FOREST PRODUCTS | 1196
320180601 | 1 | ASPEN DU BLANC | 27 | 414 | 11403.17 | 11403.17 | 2007-09-27 | 2009-11-30 | 2009-11-30 | 201 | K & B ENTERPRISES | 795
321060601 | 1 | HERMIT LAKE GRAVEL PIT | 79.5 | 2316.4 | 71381.3 | 7138.13 | 2007-07-05 | 2009-11-30 | 2009-11-30 | 201 | MINERICK LOGGING, INC | 879
321040601 | 1 | HELEN LAKE DUMPSTERS SALE | 79.8 | 2359 | 103966.8 | 103966.8 | 2006-10-06 | 2009-11-30 | 2009-11-30 | 201 | MINERICK LOGGING, INC | 1151
321100601 | 1 | OUT SOUTH SALE | 24 | 343 | 11245.15 | 1124.52 | 2007-05-17 | 2009-11-30 | 2009-11-30 | 201 | HOLLI FOREST PRODUCTS, INC. | 928
320040601 | 1 | M-35 HARDWOOD | 31.1 | 368.9 | 10439.05 | 1043.91 | 2007-09-12 | 2009-11-30 | 2009-11-30 | 201 | K & B ENTERPRISES | 810
320080601 | 1 | BOBS CREEK ROAD SALE | 58.7 | 1037.84 | 31503.11 | 23942.36 | 2007-04-16 | 2009-11-30 | 2009-11-30 | 201 | JACOBSON LOGGING, INC. | 959
320010501 | 1 | MILLER CREEK SOUTH | 55 | 608.8 | 26478.98 | 2647.9 | 2006-07-25 | 2009-11-30 | 2009-11-30 | 201 | ST. JOHN FOREST PRODUCTS, INC. | 1224
320070601 | 1 | FARMER LAKE SALE | 155.5 | 2177.68 | 113676.95 | 113676.95 | 2006-08-24 | 2009-11-30 | 2009-11-30 | 201 | SANVILLE LOGGING, INC. | 1194
320030601 | 1 | POLE LINE SALE | 16.3 | 280 | 6486.75 | 6486.75 | 2007-08-03 | 2009-11-30 | 2009-11-30 | 201 | VERSO PAPER | 850
323140701 | 1 | SHOP SALE | 10.5 | 112.8 | 4532 | 453.2 | 2007-09-12 | 2009-11-30 | 2009-11-30 | 201 | GAZAN TIMBER CONTRACTING, INC. | 810
320230501 | 1 | STACK GRADE NORTH | 42.7 | 733.2 | 37549.3 | 3754.93 | 2006-07-14 | 2009-11-30 | 2009-11-30 | 201 | LAFLEUR FOREST PRODUCTS | 1235
321300601 | 1 | BRYAN CREEK PINE/BIRCH SALE | 61.1 | 1262 | 35256.55 | 3525.66 | 2007-09-27 | 2009-11-30 | 2009-11-30 | 201 | K & B ENTERPRISES | 795
323050601 | 2 | SOUTH BOAR'S NEST SALE | 59 | 514.8 | 10125.98 | 5186.48 | 2007-11-21 | 2009-05-31 | 2010-05-31 | 383 | TRIEST FOREST PRODUCTS, INC | 922
323160601 | 1 | BUSHY CREEK HARDWOOD SALE | 84 | 1051 | 24372.42 | 24372.42 | 2007-04-25 | 2010-05-31 | 2010-05-31 | 383 | HEIDTMAN LOGGING, INC. | 1132
320150601 | 1 | LONE PINE CREEK SALE | 25 | 305.2 | 7936.8 | 793.68 | 2007-12-19 | 2010-05-31 | 2010-05-31 | 383 | GAZAN TIMBER CONTRACTING, INC. | 894
323190601 | 1 | O'NEIL CREEK SALE | 287.6 | 5198.5 | 158671.5 | 15867.15 | 2007-09-21 | 2010-05-31 | 2010-05-31 | 383 | SANVILLE LOGGING, INC. | 983
323220601 | 1 | KAWBAWGAM SALE | 103.1 | 1370.8 | 40371.4 | 4037.14 | 2007-09-21 | 2010-05-31 | 2010-05-31 | 383 | SANVILLE LOGGING, INC. | 983
323220701 | 1 | M-28 PATCHES. | 21.1 | 308 | 7080 | 708 | 2007-11-07 | 2010-05-31 | 2010-05-31 | 383 | ROY NELSON JR&SON FOR PROD INC | 936
320180701 | 1 | PERRIN CENTRAL SALE | 84.8 | 1859 | 61006.22 | 6100.62 | 2007-09-25 | 2010-05-31 | 2010-05-31 | 383 | JACOBSON LOGGING, INC. | 979
323250601 | 1 | BURMA COUNTRY MIX | 82 | 1253 | 27431.2 | 2743.12 | 2007-07-18 | 2010-05-31 | 2010-05-31 | 383 | GAZAN TIMBER CONTRACTING, INC. | 1048
320200601 | 1 | DEADHORSE AND DEERFLIES | 90 | 1659.3 | 44629.33 | 26777.6 | 2007-07-11 | 2010-05-31 | 2010-05-31 | 383 | GAZAN TIMBER CONTRACTING, INC. | 1055
323010701 | 1 | GARLIC SALE | 32.2 | 255.8 | 7720 | 772 | 2007-11-20 | 2010-05-31 | 2010-05-31 | 383 | CMP HOLDINGS DBA VERSO PAPER | 923
320210701 | 1 | BROKEN HATCHET | 36 | 140 | 8375.04 | 837.5 | 2007-07-18 | 2010-05-31 | 2010-05-31 | 383 | C.J. LOGGING | 1048
320090601 | 1 | JERRY'S TRESPASS | 54 | 573.6 | 29888.15 | 2988.82 | 2007-05-10 | 2010-05-31 | 2010-05-31 | 383 | LAFLEUR FOREST PRODUCTS | 1117
320270701 | 1 | ALMOST ESKY ASPEN | 15 | 416.3 | 8619.75 | 861.98 | 2007-10-17 | 2010-05-31 | 2010-05-31 | 383 | KANERVA FOREST PRODUCTS, INC. | 957
323330701 | 2 | FLATROCK SWAMP ROAD SALE | 21.9 | 551 | 7940.1 | 794.01 | 2008-04-11 | 2010-05-31 | 2010-05-31 | 383 | TRIEST FOREST PRODUCTS, INC | 780
321260701 | 2 | DALTON SALE | 23.1 | 258.6 | 7400 | 740 | 2007-11-07 | 2010-05-31 | 2010-05-31 | 383 | TRIEST FOREST PRODUCTS, INC | 936
320190601 | 1 | JIMMY'S JAUNT | 53 | 437.8 | 13357.69 | 1335.77 | 2007-06-22 | 2010-05-31 | 2010-05-31 | 383 | GIGUERE LOGGING, INC | 1074
320230601 | 1 | TROUT LAKE ROAD PIT SALE | 214.4 | 2224.7 | 100749.01 | 73546.78 | 2007-06-11 | 2010-05-31 | 2010-05-31 | 383 | T-N-T TIMBER PRODUCERS | 1085
320230701 | 1 | FOOD PLOT SALE | 23.4 | 315.5 | 10512.89 | 1051.29 | 2007-07-05 | 2010-05-31 | 2010-05-31 | 383 | ST. JOHN FOREST PRODUCTS, INC. | 1061
320220701 | 1 | HILLTOP SALE | 20.2 | 225.7 | 6878.45 | 687.85 | 2007-08-31 | 2010-05-31 | 2010-05-31 | 383 | ST. JOHN FOREST PRODUCTS, INC. | 1004
320340701 | 1 | SQUIRREL HAVEN SALE | 3.2 | 17.64 | 249.92 | 24.99 | 2008-09-04 | 2010-11-30 | 2010-11-30 | 566 | C.J. LOGGING | 817
320300701 | 1 | SMALL JOHNSON CREEK SALE | 3.2 | 27.4 | 614.59 | 61.46 | 2007-09-28 | 2010-11-30 | 2010-11-30 | 566 | C.J. LOGGING | 1159
321130701 | 1 | NO NAME SALE | 35 | 611 | 15373.96 | 15373.96 | 2008-01-03 | 2010-11-30 | 2010-11-30 | 566 | HEIDTMAN LOGGING, INC. | 1062
321200801 | 1 | SHARPTAIL JACK PINE | 34 | 620 | 28685.6 | 2868.56 | 2008-06-10 | 2010-11-30 | 2010-11-30 | 566 | CHOLEWA FOREST PRODUCTS | 903
320100701 | 1 | BACKYARD JACK PINE | 9.4 | 116 | 4622.39 | 462.44 | 2007-12-14 | 2010-11-30 | 2010-11-30 | 566 | KANERVA FOREST PRODUCTS, INC. | 1082
321160701 | 1 | WHERE'S WARREN | 82 | 1944 | 71776 | 7177.6 | 2007-10-15 | 2010-11-30 | 2010-11-30 | 566 | LAFLEUR FOREST PRODUCTS | 1142
320110701 | 1 | KNUDSEN ROAD SALE | 24.3 | 300.01 | 10254.37 | 1025.44 | 2007-12-14 | 2010-11-30 | 2010-11-30 | 566 | GAZAN TIMBER CONTRACTING, INC. | 1082
321140701 | 1 | NORTH FLOPPER SALE | 115.5 | 1939.1 | 56501.42 | 5650.14 | 2007-11-16 | 2010-11-30 | 2010-11-30 | 566 | ROY NELSON JR&SON FOR PROD INC | 1110
321120701 | 1 | HIGH-LOW SALE | 62 | 1207 | 32037.75 | 3203.78 | 2007-10-31 | 2010-11-30 | 2010-11-30 | 566 | MINERICK LOGGING, INC | 1126
320240701 | 1 | CAMP 19 SALE | 49.8 | 592.3 | 18958.25 | 1895.83 | 2007-10-15 | 2010-11-30 | 2010-11-30 | 566 | LAFLEUR FOREST PRODUCTS | 1142
321110701 | 1 | MOTHER GOOSE MIX | 59 | 1082 | 32082.13 | 3208.21 | 2008-01-03 | 2010-11-30 | 2010-11-30 | 566 | HOLLI FOREST PRODUCTS, INC. | 1062
320150701 | 1 | BOB'S LAKE ASPEN/BIRCH | 8.4 | 103.07 | 2861.32 | 286.13 | 2007-12-19 | 2010-11-30 | 2010-11-30 | 566 | C.J. LOGGING | 1077
320170701 | 2 | DENN'S OLD CAMP HARDWOOD | 14.6 | 141.6 | 3722.94 | 372.29 | 2007-12-27 | 2010-11-30 | 2010-11-30 | 566 | TRIEST FOREST PRODUCTS, INC | 1069
321070701 | 1 | FRANCOEUR PINE SALE | 86.5 | 1701 | 75474.27 | 7547.43 | 2007-09-26 | 2010-11-30 | 2010-11-30 | 566 | HOLLI FOREST PRODUCTS, INC. | 1161
321070601 | 1 | FLOODWOOD SOFTWOOD SALE | 67.3 | 2143 | 82319.53 | 8231.95 | 2007-07-16 | 2010-05-31 | 2010-11-30 | 566 | MINERICK LOGGING, INC | 1233
321050601 | 1 | PORTERFIELD ROAD ELF SALE | 38.4 | 1125 | 42651.75 | 4265.18 | 2007-05-03 | 2010-11-30 | 2010-11-30 | 566 | FRANK'S LOGGING | 1307
320110801 | 1 | WEST IS BEST | 41 | 618.3 | 21600.13 | 2160.01 | 2008-07-09 | 2010-11-30 | 2010-11-30 | 566 | MINERICK LOGGING, INC | 874
320100801 | 1 | ESC RIVER MIX | 51 | 665.9 | 18500.44 | 1850.04 | 2009-05-12 | 2011-05-30 | 2011-05-30 | 747 | K & K LOGGING | 748
320030801 | 1 | 438 SPLIT | 12 | 59.6 | 1888.94 | 188.89 | 2009-03-26 | 2011-05-30 | 2011-05-30 | 747 | C.J. LOGGING | 795
320190702 | 1 | SNOWSHOE BLUES | 33 | 711 | 13773.14 | 1377.31 | 2007-12-04 | 2011-05-31 | 2011-05-31 | 748 | GIGUERE LOGGING, INC | 1274
320140701 | 1 | HAYWIRE HARDWOODS | 178 | 1446.5 | 73462.42 | 7346.24 | 2007-12-14 | 2011-05-31 | 2011-05-31 | 748 | LAFLEUR FOREST PRODUCTS | 1264
320050801 | 2 | CATS & JAMMERS | 52 | 685 | 18936.2 | 1893.62 | 2008-05-30 | 2011-05-31 | 2011-05-31 | 748 | TRIEST FOREST PRODUCTS, INC | 1096
321190801 | 1 | TRASH CAN FIR | 36 | 448 | 10301.7 | 1030.71 | 2008-06-27 | 2011-05-31 | 2011-05-31 | 748 | MINERICK LOGGING, INC | 1068
320250501 | 2 | CR-TWO | 55 | 923.8 | 31157.08 | 3115.71 | 2007-04-16 | 2011-05-31 | 2011-05-31 | 748 | VERSO PAPER | 1506
321040701 | 1 | WOLF TIMBER SALE | 57.5 | 873.8 | 20346.89 |  | 2008-06-19 | 2011-05-31 | 2011-05-31 | 748 | HERITAGE TIMBER PRODUCTS | 1076
321030701 | 1 | WOLF LAKE HARDWOOD | 39.3 | 341.4 | 8413.55 | 841.36 | 2008-03-18 | 2011-05-31 | 2011-05-31 | 748 | S.D. WARREN COMPANY DBA SAPPI | 1169
323040601 | 2 | NORTH BOAR'S NEST | 184 | 2571.2 | 48697.65 | 4869.77 | 2007-11-21 | 2011-05-31 | 2011-05-31 | 748 | TRIEST FOREST PRODUCTS, INC | 1287
321020701 | 1 | SAND R. MAPLE SALE | 132.4 | 1944 | 73007.31 | 7300.73 | 2008-04-30 | 2011-05-31 | 2011-05-31 | 748 | ROY NELSON JR&SON FOR PROD INC | 1126
323050801 | 1 | JJ'S GOLD MINE SALE | 48.8 | 437.6 | 13571.4 | 1357.14 | 2009-03-11 | 2011-05-31 | 2011-05-31 | 748 | S.D. WARREN COMPANY DBA SAPPI | 811
321010701 | 1 | TOWERING HARDWOOD SALE | 98.5 | 1244.8 | 36381.54 | 3638.15 | 2008-04-07 | 2011-05-31 | 2011-05-31 | 748 | MINERICK LOGGING, INC | 1149
320260701 | 2 | CHARLIE'S CAMP | 184 | 3890.4 | 125120.6 | 12512.06 | 2007-11-20 | 2011-05-31 | 2011-05-31 | 748 | TRIEST FOREST PRODUCTS, INC | 1288
321160801 | 1 | HEMMINGS LAKE CONGLOMERATE | 51 | 887 | 36012.73 | 3601.27 | 2009-05-13 | 2011-05-31 | 2011-05-31 | 748 | HOLLI FOREST PRODUCTS, INC. | 748
321300801 | 1 | HAWKINS POND ELF TRACKS | 58 | 1165.4 | 45780.4 | 4578.04 | 2009-03-20 | 2011-05-31 | 2011-05-31 | 748 | HOLLI FOREST PRODUCTS, INC. | 802
320060701 | 1 | SWAMPBUCK ASPEN | 36 | 859 | 21484.8 | 2148.48 | 2008-03-21 | 2011-11-30 | 2011-11-30 | 931 | SANVILLE LOGGING, INC. | 1349
321180801 | 1 | MASSED PRODUCTION OAK | 139 | 1695.4 | 38677.25 | 3867.73 | 2009-03-20 | 2011-11-30 | 2011-11-30 | 931 | LAFLEUR FOREST PRODUCTS | 985
320080801 | 1 | SECTION 32 ROAD ASPEN | 44 | 1021.9 | 35437.34 | 3543.73 | 2009-02-13 | 2011-11-30 | 2011-11-30 | 931 | J. CAREY LOGGING, INC. | 1020
321210801 | 1 | TWO STAND JACK SALE | 39 | 552.88 | 20221.25 | 2022.13 | 2008-08-13 | 2011-11-30 | 2011-11-30 | 931 | SANVILLE LOGGING, INC. | 1204
320090801 | 1 | CHANDLER BROOK ASPEN | 43 | 718 | 23687.1 | 2368.71 | 2008-07-09 | 2011-11-30 | 2011-11-30 | 931 | MINERICK LOGGING, INC | 1239
321220801 | 1 | KORPI'S CUT | 67 | 1142 | 34779.37 | 3477.94 | 2008-11-05 | 2011-11-30 | 2011-11-30 | 931 | HOLLI FOREST PRODUCTS, INC. | 1120
320080901 | 1 | WEST CHANDLER MIX | 81 | 757.9 | 28746.84 | 2874.68 | 2009-05-12 | 2011-11-30 | 2011-11-30 | 931 | K & K LOGGING | 932
320080701 | 1 | RT SPECIAL | 59.7 | 1026.4 | 25028.1 | 2502.81 | 2008-01-23 | 2011-11-30 | 2011-11-30 | 931 | GIGUERE LOGGING, INC | 1407
321230801 | 2 | C.R. MU PINE | 40 | 657 | 19414.75 | 19414.75 | 2008-07-09 | 2011-11-30 | 2011-11-30 | 931 | HEIDTMAN LOGGING, INC. | 1239
320070701 | 1 | SWAMP BUCK HARDWOODS | 59.2 | 670.4 | 16934.4 | 1693.44 | 2007-12-14 | 2011-11-30 | 2011-11-30 | 931 | KANERVA FOREST PRODUCTS, INC. | 1447
320060801 | 1 | BILSKY LAKE ASPEN | 43 | 821.98 | 35053.14 | 3505.31 | 2008-07-21 | 2011-11-30 | 2011-11-30 | 931 | MINERICK LOGGING, INC | 1227
320120801 | 1 | PARKER END SALE | 158.3 | 2921.1 | 121437.37 | 12143.74 | 2008-07-28 | 2011-11-30 | 2011-11-30 | 931 | LAFLEUR FOREST PRODUCTS | 1220
320050701 | 1 | MUD CREEK MIX | 124.5 | 1010.4 | 22584 | 2258.4 | 2008-04-02 | 2011-11-30 | 2011-11-30 | 931 | GIGUERE LOGGING, INC | 1337
320030701 | 1 | STACK GRADE 07 | 48.8 | 503.8 | 11028.1 | 1102.81 | 2008-03-21 | 2011-11-30 | 2011-11-30 | 931 | SANVILLE LOGGING, INC. | 1349
320010801 | 1 | PBR ASPEN | 108 | 2738.4 | 98683.99 | 9868.4 | 2009-01-21 | 2011-11-30 | 2011-11-30 | 931 | MINERICK LOGGING | 1043
320010701 | 1 | LATHROP SALE | 84.3 | 1388.2 | 32874 | 3287.4 | 2008-01-15 | 2011-11-30 | 2011-11-30 | 931 | GAZAN TIMBER CONTRACTING, INC. | 1415
321240801 | 1 | MCC SALE | 40 | 815 | 23588.7 | 2358.87 | 2008-11-14 | 2011-11-30 | 2011-11-30 | 931 | LUCAS LOGGING | 1111
321070801 | 1 | AMVETS JACK PINE | 14 | 301 | 12843.67 | 1284.37 | 2009-05-13 | 2011-11-30 | 2011-11-30 | 931 | J. CAREY LOGGING, INC. | 931
320210801 | 1 | WERNER BRIDGE SALE | 80.7 | 926.7 | 31716.55 | 3171.66 | 2008-11-05 | 2011-11-30 | 2011-11-30 | 931 | KANERVA FOREST PRODUCTS, INC. | 1120
321010801 | 1 | ANDERSON HOMESTEAD SALE | 204 | 3516 | 150825 | 15082.52 | 2009-03-20 | 2011-11-30 | 2011-11-30 | 931 | HOLLI FOREST PRODUCTS, INC. | 985
320200801 | 1 | HIGH FENCE ASPEN | 56.2 | 587.56 | 20480.25 | 2048.03 | 2008-08-05 | 2011-11-30 | 2011-11-30 | 931 | DAVE JOHNSON LOGGING | 1212
321020801 | 1 | BENTLEY POND SALE | 158 | 3143 | 135526.16 | 13552.62 | 2009-03-20 | 2011-11-30 | 2011-11-30 | 931 | HOLLI FOREST PRODUCTS, INC. | 985
320190801 | 1 | WATSON INTERSECTION SALE | 83.8 | 859.34 | 28966.16 | 2896.62 | 2008-07-01 | 2011-11-30 | 2011-11-30 | 931 | GIGUERE LOGGING, INC | 1247
321040801 | 1 | FETCHING YELLOW DOG PINE SALE | 42.4 | 1219 | 49760 | 4976 | 2009-03-20 | 2011-11-30 | 2011-11-30 | 931 | HOLLI FOREST PRODUCTS, INC. | 985
320180801 | 1 | PIG RANCH ASPEN | 24.5 | 316.43 | 9939.8 | 993.98 | 2008-07-17 | 2011-11-30 | 2011-11-30 | 931 | LUCAS LOGGING | 1231
321150801 | 1 | POT HOLE SALE | 65.5 | 885 | 24753.85 | 2475.39 | 2009-01-21 | 2011-11-30 | 2011-11-30 | 931 | MINERICK LOGGING | 1043
321060801 | 1 | SLEEMAN POND SALE | 66 | 651.6 | 18079.77 | 1807.98 | 2009-03-20 | 2011-11-30 | 2011-11-30 | 931 | HOLLI FOREST PRODUCTS, INC. | 985
321140801 | 1 | DRAINED POND PINE | 66 | 816.77 | 33826.89 | 3382.69 | 2009-01-22 | 2011-11-30 | 2011-11-30 | 931 | HOLLI FOREST PRODUCTS, INC. | 1042
321090801 | 1 | T. SALE 109-08 | 15 | 184 | 6460.24 | 646.02 | 2009-03-20 | 2011-11-30 | 2011-11-30 | 931 | HOLLI FOREST PRODUCTS, INC. | 985
320130801 | 1 | NEIGHBOR BEN SALE | 38.2 | 640.3 | 21406.1 | 2140.61 | 2008-07-10 | 2011-11-30 | 2011-11-30 | 931 | GIGUERE LOGGING, INC | 1238
321110801 | 1 | BURSTING GROUSE | 41 | 695 | 15100.95 | 15100.95 | 2008-09-15 | 2011-11-30 | 2011-11-30 | 931 | HEIDTMAN LOGGING, INC. | 1171
321100801 | 1 | COLD TOES SALE | 63 | 1188 | 37776.99 | 3777.7 | 2008-09-24 | 2011-11-30 | 2011-11-30 | 931 | VERSO PAPER | 1162
321050801 | 1 | MIDDLE BRANCH SPLIT SALE | 54.5 | 619.2 | 26442.2 | 2644.22 | 2009-01-22 | 2011-11-30 | 2011-11-30 | 931 | HOLLI FOREST PRODUCTS, INC. | 1042
320140801 | 1 | THOMAS CAMP ASPEN | 32 | 558.63 | 16762.04 | 1676.2 | 2008-05-15 | 2011-11-30 | 2011-11-30 | 931 | GIGUERE LOGGING, INC | 1294
320170801 | 1 | HUNTERS BROOK ASPEN | 26.2 | 246.92 | 7580.6 | 758.06 | 2008-07-01 | 2011-11-30 | 2011-11-30 | 931 | GAZAN TIMBER CONTRACTING, INC. | 1247
321080801 | 1 | C. 228 JACK PINE | 20 | 311 | 13236.16 | 1323.62 | 2009-05-04 | 2011-11-30 | 2011-11-30 | 931 | HOLLI FOREST PRODUCTS, INC. | 940
320150801 | 2 | BASIN FIR/HARDWOOD | 55 | 373.15 | 17809.05 | 1780.91 | 2008-05-30 | 2011-11-30 | 2011-11-30 | 931 | TRIEST FOREST PRODUCTS, INC | 1279
320160801 | 1 | OLD LANDFILL ASPEN | 123.8 | 1949.3 | 72627.08 | 7262.71 | 2008-11-05 | 2011-11-30 | 2011-11-30 | 931 | KANERVA FOREST PRODUCTS, INC. | 1120
321070901 | 1 | PORTERFIELD LAKE SALE | 46.8 | 757.8 | 25549.22 | 2554.92 | 2009-05-04 | 2011-11-30 | 2011-11-30 | 931 | HOLLI FOREST PRODUCTS, INC. | 940
320220801 | 1 | D+D HARDWOODS | 43 | 201.1 | 5923.19 | 592.32 | 2009-03-20 | 2012-05-30 | 2012-05-30 | 1113 | ROY NELSON JR&SON FOR PROD INC | 1167
321250801 | 1 | CAMP 4 CLUSTER SALE | 55.7 | 1107 | 30247.35 | 3024.74 | 2009-03-06 | 2012-05-31 | 2012-05-31 | 1114 | HEIDTMAN LOGGING, INC. | 1182
320020801 | 1 | PBR SOUTH | 50 | 847.7 | 24510.84 | 2451.08 | 2009-05-13 | 2012-05-31 | 2012-05-31 | 1114 | J. CAREY LOGGING, INC. | 1114
320220901 | 1 | EAST CABLES MIX | 87 | 1065.4 | 30887.64 | 3088.76 | 2009-03-20 | 2012-05-31 | 2012-05-31 | 1114 | LAFLEUR FOREST PRODUCTS | 1168
320070801 | 1 | TWO COUNTY ASPEN | 70 | 1517.6 | 47941.59 | 4794.16 | 2009-04-01 | 2012-11-30 | 2012-11-30 | 1297 | MINERICK LOGGING | 1339
321270801 | 1 | SWEENY SAND SALE | 92 | 1958.96 | 48645.96 | 4864.6 | 2008-01-21 | 2012-11-30 | 2012-11-30 | 1297 | HEIDTMAN LOGGING, INC. | 1775