## 
Open Contract Analysis for the Gwinn Forest Management Unit
as of July 10, 2013
Use Page Down Key to See List of Open Sales
Nbr of
|  | Sale Expiration Status | Sales
|  | Contracts Expired | 1 | [9 empty] | Expiration | Expiration | Expiration | Expiration | Expiration
|  | 30 Days before Expiration | 0 | [9 empty] | <0 | >0 | <31 | >30 | <61
|  | 60 Days before Expiration | 0 | [9 empty] | Expiration
|  | >60 Days before Expiration | 89 | [9 empty] | >60
|  | Total | 90
|  | Contract Summary |  |  | Total | [7 empty] | Sale Number | Acres | Volume | Value | Received | Length(days)
|  | Nbr of Open Contracts |  |  | 90 | [7 empty] | > " " | > 0.00 | >0.00 | >0.00 | >0.00 | >0.00
|  | Acres of Open Contracts |  |  | 5910
|  | Open Contacts Cords |  |  | 82529
|  | Value of Open Contracts |  |  | 4203031.78
|  | Amount Received to Date |  |  | 1084499.62
|  | Amount Remaining |  |  | 3118532.16
|  | Percentage of Contract Value Received to Date |  |  | 25.8%
|  | Expiration Date Used |  |  | 2013-07-10
|  | Avg Contract Length (Years) |  |  | 3.967
Open Timber Sale Contracts sorted by Days Before Expiration
|  |  |  | Total | Current |  | Contract | Original | Current | Days |  | Current
| Cont |  |  | Cord | Contract | Amount | Issue | Expiration | Expiration | Before |  | Contract
Sale Number | Seq | Sale Name | Acres | Volume | Value | Received | Date | Date | Date | Expiration | Purchaser Name | Length(days)
320081202 | 1 | WAYMAN CABIN ROAD | 1 | 11.2 | 371.75 | 371.75 | 2013-02-21 | 2013-03-31 | 2013-03-31 | -101 | COMPASS LAND CONSULTANTS INC | 38
321111101 | 2 | PATCHY JACK SALE | 38.5 | 365 | 14825.9 | 1482.59 | 2011-06-15 | 2013-11-13 | 2013-11-13 | 126 | HEIDTMAN LOGGING, INC | 882
320011101 | 1 | KAMIKAZE PARTRIDGE | 76 | 1026 | 67253.6 | 67253.6 | 2011-09-13 | 2013-11-30 | 2013-11-30 | 143 | LAFLEUR FOREST PRODUCTS, LLC | 809
320051001 | 1 | BOB WILSON SPRUCE | 55 | 993 | 58645.84 | 5864.58 | 2011-07-08 | 2013-11-30 | 2013-11-30 | 143 | GIGUERE LOGGING, INC | 876
320061001 | 1 | HIGH BANKS HARDWOOD | 17 | 166 | 5798.45 | 579.85 | 2011-07-19 | 2013-11-30 | 2013-11-30 | 143 | MOTTO LOGGING | 865
320070801 | 1 | TWO COUNTY ASPEN | 70 | 1517.6 | 50338.67 | 50338.67 | 2009-04-01 | 2012-11-30 | 2013-11-30 | 143 | ROBERT MINERICK | 1704
320110901 | 1 | CAMP 10 MIX | 107 | 2352 | 96320.44 | 13760.07 | 2010-04-26 | 2012-11-30 | 2013-11-30 | 143 | MINERICK LOGGING, INC. | 1314
320121001 | 1 | KAUPPILA ACCESS HARDWOODS | 27 | 233.2 | 7497.45 | 749.75 | 2010-07-09 | 2013-11-30 | 2013-11-30 | 143 | DIVERSIFIED FORESTRY | 1240
321041101 | 2 | FLAT ROCK RD. MIX | 26 | 362 | 16043.5 | 1604.35 | 2011-05-18 | 2013-11-30 | 2013-11-30 | 143 | SANVILLE LOGGING, INC. | 927
321061101 | 1 | FLAT ROCK BIRCH SALE | 47.1 | 931.6 | 47148.54 | 4714.85 | 2011-11-22 | 2013-11-30 | 2013-11-30 | 143 | MINERICK LOGGING, INC. | 739
321101001 | 1 | BRYAN PINE SALE | 135 | 2313 | 164145.45 | 82072.73 | 2011-04-15 | 2013-11-30 | 2013-11-30 | 143 | MINERICK LOGGING, INC. | 960
321120901 | 1 | BLUEBERRY PINE SALE | 51.5 | 862 | 50655.76 | 5065.58 | 2011-11-22 | 2013-11-30 | 2013-11-30 | 143 | MINERICK LOGGING, INC. | 739
321131001 | 1 | TRIPLE A WHITE SALE | 137 | 1841 | 74073.14 | 74073.14 | 2011-02-07 | 2013-11-30 | 2013-11-30 | 143 | HOLLI FOREST PRODUCTS, INC. | 1027
321031101 | 1 | HEART LAKE SALE | 109 | 1969 | 78776.64 | 7877.66 | 2011-12-14 | 2014-05-30 | 2014-05-30 | 324 | HOLLI FOREST PRODUCTS, INC. | 898
320031001 | 1 | CROOKED LAKE ASPEN | 29 | 523 | 22759.8 | 22759.8 | 1911-02-09 | 1913-05-31 | 2014-05-31 | 325 | LAFLEUR FOREST PRODUCTS, LLC | 37732
320041001 | 1 | WHITEYS HILL | 83 | 284.8 | 33647.74 | 10576.86 | 2010-08-03 | 2013-05-31 | 2014-05-31 | 325 | RON GRAVES LOGGING | 1397
320050901 | 1 | FERGIE HARDWOODS | 100 | 492.5 | 28111.12 | 9098.77 | 2010-05-07 | 2013-05-31 | 2014-05-31 | 325 | RON GRAVES LOGGING | 1485
320051101 | 1 | KC MIX | 76 | 631.4 | 72976.3 | 7297.63 | 2011-10-04 | 2014-05-31 | 2014-05-31 | 325 | LAFLEUR FOREST PRODUCTS, LLC | 970
320091001 | 1 | ROSS CREEK HARDWOODS | 116 | 855.6 | 42004.66 | 6004.66 | 2010-11-15 | 2013-05-31 | 2014-05-31 | 325 | MINERICK LOGGING, INC. | 1293
320131101 | 1 | SAARIS CAMP | 124 | 772 | 69335.1 | 42987.76 | 2011-11-29 | 2014-05-31 | 2014-05-31 | 325 | K & K LOGGING | 914
320151101 | 1 | ASPEN PATCHES PLUS | 37 | 660.6 | 28919.1 | 8675.72 | 2011-01-19 | 2014-05-31 | 2014-05-31 | 325 | K & K LOGGING | 1228
320161001 | 1 | HAMILTON ASPEN | 117 | 2135 | 107630.78 | 15375.83 | 2010-07-02 | 2013-05-31 | 2014-05-31 | 325 | MINERICK LOGGING, INC. | 1429
320171001 | 1 | STRETCHS CAMP | 33 | 293 | 11015.79 | 1573.68 | 2011-07-11 | 2013-05-31 | 2014-05-31 | 325 | RALPH BUGAY & SON LOGGING | 1055
320211101 | 1 | PIKE LAKE CAMPGROUND | 9 | 95 | 4527.25 | 470.73 | 2012-06-20 | 2014-05-31 | 2014-05-31 | 325 | LAFLEUR FOREST PRODUCTS, LLC | 710
321011101 | 1 | CLOWRY-BURMA SPF | 66 | 1269 | 56649.97 | 5665 | 2012-03-19 | 2014-05-31 | 2014-05-31 | 325 | MINERICK LOGGING, INC. | 803
321021001 | 1 | THOMAS LAKE HARDWOOD | 123 | 1130.8 | 27985.86 | 3997.98 | 2011-05-12 | 2013-05-31 | 2014-05-31 | 325 | J. CAREY LOGGING INC | 1115
321021101 | 1 | ISLAND LAKE ROAD PINE | 34 | 724 | 42229.09 | 4222.91 | 2012-04-10 | 2014-05-31 | 2014-05-31 | 325 | MINERICK LOGGING, INC. | 781
321051101 | 1 | FLAT ROCK PINE ISLANDS | 34 | 577 | 24146.11 | 2414.61 | 2011-12-14 | 2014-05-31 | 2014-05-31 | 325 | HOLLI FOREST PRODUCTS, INC. | 899
321091101 | 1 | VOELKER RED PINE-SPRUCE | 76.5 | 900.4 | 48938.71 | 4893.87 | 2011-12-14 | 2014-05-31 | 2014-05-31 | 325 | HOLLI FOREST PRODUCTS, INC. | 899
321151001 | 2 | VOELKER PLAINS JACK PINE-ASPEN | 53 | 276 | 10094.6 | 1514.19 | 2011-02-09 | 2013-05-31 | 2014-05-31 | 325 | HEIDTMAN LOGGING, INC | 1207
321181101 | 2 | K.I.H. SALE | 35 | 383.4 | 12935.92 | 1293.59 | 2012-03-19 | 2014-05-31 | 2014-05-31 | 325 | SANVILLE LOGGING, INC. | 803
321260901 | 1 | SAND RIVER BLADE SALE | 175.8 | 3876.4 | 151455.77 | 151455.77 | 2010-04-26 | 2013-05-31 | 2014-05-31 | 325 | HEIDTMAN LOGGING, INC | 1496
323021001 | 1 | OUT NORTH SALE | 56 | 823 | 33084.21 | 16316.38 | 2011-05-10 | 2013-05-31 | 2014-05-31 | 325 | HOLLI FOREST PRODUCTS, INC. | 1117
323021101 | 1 | 218 RED ASPEN | 81 | 671 | 19647.33 | 1964.73 | 2012-10-05 | 2014-05-31 | 2014-05-31 | 325 | MINERICK LOGGING, INC. | 603
323031001 | 1 | VAN RIPER LAKES | 20 | 322.4 | 10509.1 | 1050.91 | 2012-05-24 | 2014-05-31 | 2014-05-31 | 325 | PLUM CREEK MARKETING, INC. | 737
323041101 | 2 | DOUBLE CAMERA ASPEN | 35 | 275 | 13610.1 | 13610.1 | 2012-04-10 | 2014-05-31 | 2014-05-31 | 325 | HEIDTMAN LOGGING, INC | 781
323051101 | 1 | HEMMINGS EXTENDED ASPEN | 31 | 666 | 32788.83 | 3278.88 | 2012-04-16 | 2014-05-31 | 2014-05-31 | 325 | MINERICK LOGGING, INC. | 775
323031101 | 1 | BBR NORTH | 23 | 369 | 12175.49 | 1217.55 | 2012-03-19 | 2014-11-01 | 2014-11-01 | 479 | MINERICK LOGGING, INC. | 957
320031101 | 1 | BLACKED OUT SPRUCE | 28 | 602 | 37263.51 | 3726.35 | 2011-08-09 | 2014-11-30 | 2014-11-30 | 508 | BRIAN CHOLEWA LOGGING | 1209
320031201 | 1 | ESCANABA R. CAMPSITE ASPEN | 20 | 299.9 | 12766 | 1276.6 | 2012-05-23 | 2014-11-30 | 2014-11-30 | 508 | LAFLEUR FOREST PRODUCTS, LLC | 921
320041101 | 1 | SHAMROCK GATE ASPEN | 82 | 1178 | 67945.45 | 6794.55 | 2011-09-13 | 2014-11-30 | 2014-11-30 | 508 | LAFLEUR FOREST PRODUCTS, LLC | 1174
320061101 | 1 | SESQUICENTENNIAL ASPEN | 30 | 802 | 50204.25 | 5020.43 | 2011-09-06 | 2014-11-30 | 2014-11-30 | 508 | LAFLEUR FOREST PRODUCTS, LLC | 1181
320111101 | 1 | WAYS ACCESS ASPEN/FIR | 17 | 252 | 9090.45 | 909.05 | 2011-09-08 | 2014-11-30 | 2014-11-30 | 508 | SANVILLE LOGGING, INC. | 1179
321071101 | 1 | FLAT ROCK CONGLOMERATE SALE | 71 | 1279 | 76161.55 | 7616.16 | 2012-04-16 | 2014-11-30 | 2014-11-30 | 508 | MINERICK LOGGING, INC. | 958
321121101 | 1 | CHARLIE CHAIN ASPEN | 84 | 1231 | 70115.68 | 7011.57 | 2012-04-30 | 2014-11-30 | 2014-11-30 | 508 | MINERICK LOGGING, INC. | 944
321151101 | 1 | DOWNUNDER JACK PINE | 77 | 2064 | 162131.4 | 16213.14 | 2012-08-07 | 2014-11-30 | 2014-11-30 | 508 | LAFLEUR FOREST PRODUCTS, LLC | 845
320011201 | 1 | 4 PT HARDWOODS | 60 | 389.8 | 31204.2 | 12169.64 | 2012-08-21 | 2015-05-31 | 2015-05-31 | 690 | RON GRAVES LOGGING | 1013
320051201 | 1 | ESCANABA RIVER RD #2 | 31 | 561.5 | 21359.21 | 2135.92 | 2012-06-11 | 2015-05-31 | 2015-05-31 | 690 | MINERICK LOGGING, INC. | 1084
320061201 | 1 | ESCANABA RIVER RD #1 | 61 | 1154 | 60259 | 6025.9 | 2012-05-23 | 2015-05-31 | 2015-05-31 | 690 | LAFLEUR FOREST PRODUCTS, LLC | 1103
320071101 | 1 | E. 557 PINE BLOCKS | 47 | 743.2 | 59618.2 | 26828.19 | 2011-09-08 | 2015-05-31 | 2015-05-31 | 690 | GIGUERE LOGGING, INC | 1361
320071201 | 1 | DADS PLACE ASPEN | 23 | 347.5 | 16217.9 | 1621.79 | 2012-05-23 | 2015-05-31 | 2015-05-31 | 690 | LAFLEUR FOREST PRODUCTS, LLC | 1103
320081101 | 1 | W. 557 PINE BLOCKS | 53 | 597.8 | 47110.8 | 47110.8 | 2011-09-08 | 2015-05-31 | 2015-05-31 | 690 | GIGUERE LOGGING, INC | 1361
320091201 | 1 | SOOTH CYR | 47 | 746.4 | 30091.8 | 3009.18 | 2012-08-10 | 2015-05-31 | 2015-05-31 | 690 | JEFF GUDWER FOREST PRODUCTS | 1024
320111201 | 1 | SWEET CREEK MAPLE | 23 | 173.2 | 6911.55 | 691.16 | 2013-01-17 | 2015-05-31 | 2015-05-31 | 690 | ROY NELSON JR & SON FOR. PROD. | 864
320141001 | 1 | DEADHORSE CREEK HARDWOODS | 177 | 1184.6 | 36531.3 | 15811.06 | 2011-07-12 | 2015-05-31 | 2015-05-31 | 690 | WILLIAMS SPECIALTY WOODS | 1419
320141101 | 1 | ROUGH RIDERS | 58 | 1354 | 77535.6 | 7753.56 | 2012-01-19 | 2015-05-31 | 2015-05-31 | 690 | LAFLEUR FOREST PRODUCTS, LLC | 1228
320151201 | 1 | LATHROP HARDWOODS | 50 | 268.8 | 13261.8 | 1326.18 | 2013-03-06 | 2015-05-31 | 2015-05-31 | 690 | ROY NELSON JR & SON FOR. PROD. | 816
320161101 | 1 | PARKER SPUR BEAR BAIT HARDWOOD | 41 | 336 | 14522.25 | 1452.23 | 2012-07-02 | 2015-05-31 | 2015-05-31 | 690 | K & K LOGGING | 1063
320171201 | 1 | LATE SUMMER SALE | 47 | 1176.4 | 40122.75 | 4012.28 | 2013-03-14 | 2015-05-31 | 2015-05-31 | 690 | EARL ST. JOHN FOREST PROD, INC | 808
320181101 | 1 | CARLSHEND HARDWOODS | 97 | 435.4 | 29995.5 | 2999.55 | 2012-05-04 | 2015-05-31 | 2015-05-31 | 690 | GIGUERE LOGGING, INC | 1122
320181201 | 1 | HIDDEN VALLI HARDWOODS | 37 | 361.6 | 14346.88 | 1434.69 | 2013-01-18 | 2015-05-31 | 2015-05-31 | 690 | HILL LOGGING INC | 863
320191101 | 1 | JOHNSON BASIN HARDWOODS | 59 | 581.4 | 24806.04 | 2480.6 | 2012-05-08 | 2015-05-31 | 2015-05-31 | 690 | ROY NELSON JR & SON FOR. PROD. | 1118
320201101 | 1 | CHAINING ASPEN | 86 | 797 | 44801.11 | 4480.11 | 2012-04-30 | 2015-05-31 | 2015-05-31 | 690 | MINERICK LOGGING, INC. | 1126
320221101 | 1 | VESSEL CAMP REVISED | 28 | 75 | 2667.9 | 266.79 | 2012-05-23 | 2015-05-31 | 2015-05-31 | 690 | RON GRAVES LOGGING | 1103
321121201 | 1 | STATION SOFTWOODS SALE | 61 | 1077 | 83561.06 | 8356.11 | 2012-10-05 | 2015-05-31 | 2015-05-31 | 690 | MINERICK LOGGING, INC. | 968
321131101 | 1 | CHARLIE ASPEN THICKETS | 105 | 1755 | 86272.04 | 8627.2 | 2012-06-20 | 2015-05-31 | 2015-05-31 | 690 | LAFLEUR FOREST PRODUCTS, LLC | 1075
321141101 | 1 | CHARLIE LAKES VIEW | 67 | 846 | 36568.94 | 3656.89 | 2012-07-02 | 2015-05-31 | 2015-05-31 | 690 | MINERICK LOGGING, INC. | 1063
321161201 | 1 | DORROW CREEK SALE | 79 | 1310 | 41487.9 | 4148.79 | 2012-10-17 | 2015-05-31 | 2015-05-31 | 690 | HEIDTMAN LOGGING, INC | 956
321201101 | 1 | SAND RIVER RUN SALE | 107 | 895.9 | 44968.45 | 4496.85 | 2012-02-06 | 2015-05-31 | 2015-05-31 | 690 | TRIEST FOREST PRODUCTS, INC. | 1210
323251201 | 1 | BURMA COUNTRY MIX #2 | 82 | 1253 | 24826 | 2482.6 | 2012-09-21 | 2015-05-31 | 2015-05-31 | 690 | WILLIAMS SPECIALTY WOODS | 982
323291201 | 1 | MT. HARLOW SALE | 60.6 | 889.4 | 23529.39 | 2352.94 | 2012-11-26 | 2015-05-31 | 2015-05-31 | 690 | TRIEST FOREST PRODUCTS, INC. | 916
321071201 | 1 | HARRIS LAKE HARDWOOD | 23 | 128 | 4246 | 424.6 | 2013-03-06 | 2015-11-15 | 2015-11-15 | 858 | VALIQUETTE HARVESTING | 984
320011301 | 1 | ANDERSON LAKE ASPEN | 78 | 1572 | 98769.95 | 9877 | 2013-06-27 | 2015-11-30 | 2015-11-30 | 873 | K & K LOGGING | 886
320041201 | 1 | OLD ELF ASPEN MIX | 29 | 417 | 19396.4 | 3491.36 | 2013-02-21 | 2015-11-30 | 2015-11-30 | 873 | K & K LOGGING | 1012
320141201 | 1 | 557/438 | 120 | 2320 | 104086.8 | 73289.39 | 2012-11-28 | 2015-11-30 | 2015-11-30 | 873 | SANVILLE LOGGING, INC. | 1097
320161201 | 1 | BASS LAKE TRAILHEAD ASPEN | 67 | 972 | 48177.05 | 8671.87 | 2013-02-21 | 2015-11-30 | 2015-11-30 | 873 | K & K LOGGING | 1012
321011201 | 1 | A CUBED SALE | 69 | 1051.2 | 44389.94 | 4438.99 | 2013-06-10 | 2015-11-30 | 2015-11-30 | 873 | TIMBER PRODUCTS COMPANY | 903
321041201 | 1 | CHAIN OF LAKES ASPEN | 47 | 615.6 | 25352.07 | 25352.07 | 2012-11-26 | 2015-11-30 | 2015-11-30 | 873 | TRIEST FOREST PRODUCTS, INC. | 1099
321061201 | 1 | LOTTO LAKE HARDWOOD | 45 | 174.4 | 15740.18 | 1574.02 | 2013-02-25 | 2015-11-30 | 2015-11-30 | 873 | TRIEST FOREST PRODUCTS, INC. | 1008
321081201 | 1 | STANDBY ASPEN | 61 | 747.4 | 29729.85 | 2972.99 | 2012-10-08 | 2015-11-30 | 2015-11-30 | 873 | SANVILLE LOGGING, INC. | 1148
321091201 | 1 | BRYAN PINE PATCHES | 74 | 1733.9 | 133142.13 | 13314.21 | 2013-04-23 | 2015-11-30 | 2015-11-30 | 873 | SANVILLE LOGGING, INC. | 951
321101201 | 1 | PEWEE PINE | 38 | 359.6 | 37844.9 | 3784.49 | 2013-04-08 | 2015-11-30 | 2015-11-30 | 873 | BELL TIMBER, INC. | 966
321311201 | 1 | YELLOW DOG JACK SALE | 67 | 2355 | 166560.98 | 16656.1 | 2013-05-30 | 2015-11-30 | 2015-11-30 | 873 | HOLLI FOREST PRODUCTS, INC. | 914
320021301 | 1 | ICE BEAR ASPEN | 50 | 831 | 42727.33 | 4272.73 | 2013-06-26 | 2016-05-31 | 2016-05-31 | 1056 | MINERICK LOGGING, INC. | 1070
320101201 | 1 | TROJAN HOUSE | 195 | 1787.4 | 99224.9 | 9922.49 | 2012-10-05 | 2016-05-31 | 2016-05-31 | 1056 | ROY NELSON JR & SON FOR. PROD. | 1334
320131201 | 1 | EAST WHITEFISH HDWDS | 75 | 474 | 37570 | 3757 | 2013-01-30 | 2016-05-31 | 2016-05-31 | 1056 | RON GRAVES LOGGING | 1217
321141201 | 1 | WEST ALGER HARDWOOD | 86 | 811 | 36779.76 | 3677.98 | 2012-02-11 | 2016-05-31 | 2016-05-31 | 1056 | VALIQUETTE HARVESTING | 1571
321151201 | 1 | WEST ALGER LINE SALE | 128 | 1333 | 49733.2 | 4973.32 | 2013-02-04 | 2016-05-31 | 2016-05-31 | 1056 | J. CAREY LOGGING INC | 1212
321031201 | 1 | MOOSE LUNCH | 102 | 2021 | 78830.55 | 7883.06 | 2013-06-27 | 2016-11-30 | 2016-11-30 | 1239 | SANVILLE LOGGING, INC. | 1252
321111201 | 1 | BRYAN CREEK ASPEN | 96 | 1858.8 | 83400.07 | 8340.01 | 2013-04-23 | 2016-11-30 | 2016-11-30 | 1239 | MINERICK LOGGING, INC. | 1317